[image: image1.png]STATE LOAD DESPATCH CENTRE

OFFICE OF THE CHIEF LOAD DESPATCHER

ODISHA POWER TRANSMISSION CORPORATION LIMITED
GRIDCO Colony, P.O.- Mancheswar Rly. Colony, Bhubaneswar-ﬁ, FAX-0674- 2748509

CIN — U401020R2004SGC007553

No-SGM (PS)-PL-15/2016 / gl\ & &é% CU DatedQé.O7.2017

From:

The Chief Load Despatcher
SLDC, OPTCL, Bhubaneswar-17.

To:

As per distribution list

Sub: Minutes of 111" PSOC meeting held on 19.07.2017 at PTC, Chandaka,
Bhubaneswar

Sir,
Please find enclosed herewith the minutes of 111™ Power System Operational Co-

ordination meeting held on 19.07.2017 at SLDC, Bhubaneswar:
This is for your information & necessary action.

Yours faithfully;

Encl: As above : L}M
;, \Y
% ,_,./’/b\VA

Chief Load Despatcher,
SLDC, OPTCL




Odisha Power Transmission Corporation Ltd. Bhubaneswar.


Minutes of 111th PSOC meeting held on 19.07.2017 at PTC, Chandaka
List of participants is at Annexure.

CGM, SLDC welcomed all the members to the 111th PSOC meeting. In his welcome address, he highlighted the system performance for the month of June’2017 and overall power scenario of the State. He also emphasized on the power drawal, made by all the Discoms during the month. 
D.G.M. (SS), SLDC took the agenda items for discussion. 

The review proceeded as follows: 
1: Confirmation of minutes of 110th PSOC meeting held on 28.06.2017
The minutes of meeting was circulated vide letter No. SGM (PS)-Pl-15/2016/2493(44) dated 06.07.2017 to all the members and also uploaded in the SLDC website. No comment has been received from any of the member except OHPC, which was clarified in the Agenda. 
Deliberation in the meeting:
The minutes of 109th PSOC meeting was confirmed. 
PART B : SYSTEM PERFORMANCE
B1: Review of Grid Performance for the month of June’2017.
(A)  Frequency 

It was noticed that, during the month of June’17, 70.86 % of times the frequency remained in the IEGC band i.e.  49.90Hz - 50.05Hz in comparison to 69.21 % during the month of  May’17. The maximum and minimum System frequency during the month was 50.16 Hz & 49.76 Hz respectively.

 (B)  Grid demand 

Grid demand for the month of  June’17 was reviewed. The average consumption during the month was 3151MW. The maximum System demand of 4009 MW occurred on 04.06.17at 24:00 Hrs and minimum demand of 2091 MW occurred on 15.06.17 at 18:00 Hrs. 
Deliberation in the meeting

It is observed that the average demand during the month of  June’ 17 has been decreased by 255 MW while the peak demand  was decreased by 272 MW from that of May’17. The average demand during the month has been decreased by 31 MW in comparison to June’16. The energy consumption has been decreased due to change in weather condition in the State.
 (C)  Voltage Profile of important Sub Stations in OPTCL System during the month of June’17.

The Voltage profile at different 220 kV buses in OPTCL system during the month of June’17 was reviewed. 
The maximum Voltage of 245.94 kV occurred at Narendrapur. Budhipadar 220 kV bus has experienced the minimum Voltage of 193.35 kV. Bus Voltages at Samgara, Lapanga and Cuttack could not be incorporated due to non availability of energy meter in those S/Ss. The 220 kV Voltage profile of Jayanagar and Narendrapur and 400 kV Voltage profile of Meramundali bus during the month of June 2017 in 15 minute block was reviewed
Deliberation in the meeting:
Jayanagar 220 kV Voltage profile has been improved due to change of Tap position at Jeypore (PG) ICT. Narendrapur 220 kV Voltage had gone high only for one day. CGM (PP) stated that Meramundali 400 kV bus Voltage had remained above 3% of normal Voltage for which GRIDCO shall pay penalty for VAr injection. O&M may explore the installation of reactor at Meramundali as suggested by ERLDC during joint study. O&M stated that the proposal for installation of reactor will be sent to NLDC for PSDF funding. SLDC may monitor the VAr injection by generators connected to Meramundali S/S.  







 [Action: CGM (O&M) / SLDC]
(D) Loading of 220/ 132 kV Auto at 220 kV S/Ss in OPTCL system for the month of June’17.

Auto loading of all 220 kV S/Ss was reviewed. It was noticed that some of the Autos have not been provided with energy meter. 
Deliberation in the meeting:
CGM (O&M) stated that energy meters have already been reached at site. The meters could not be tested as; the testing kit is yet to be received. All meters are expected to be commissioned by end of August’17. 









        
        [Action: CGM (O&M)]

(E) DISCOM Drawal during the month of June’17 
The schedule and actual energy drawal by Discoms for the month of June’17 was reviewed. 
Deliberation in the meeting:
It was noticed that CESU had overdrawn 4.408 MU followed by NESCO 4.437 MU, while  WESCO & SOUTHCO were under drawn during the month. 

 [Action: All Distribution Utilities / SLDC]
(F) Energy Generation / import during the month of June’17 
Energy generation and exchange during the month of  June’17 was reviewed. The total quantum of energy drawn from all the generation sources including Central Sector Share and CGP/IPP support during the month was 2268 MU. 
Deliberations in the meeting
The energy demand has decreased due to improvement of weather condition in the State.
 (G) Drawal of Machhakund Power during the month of June’17
The drawal of Machhakund power during the month of June’17 was 19.509 MU, against AP drawal of 24.105 MU. 
In the 110th PSOC meeting CGM (Telecom) stated that communication port of Machhakund RTU will be replaced by 6th July’2017.

Deliberations in the meeting

SLDC stated that matching load for drawal of Machhakund share was not feasible during the month of June’2017 due to low generation. Also matching load may not be possible due to shutdown of 132 kV Rayagada-Jayanagar line for LILO at Podagada S/S.

CGM (Telecom) stated that communication port of Machhakund RTU has been replaced. 

 [Action: SLDC / CGM (Telecom)]
 (H) Under Frequency relay operation in OPTCL System during the month of June’17.

There is no UF Relay operation during the month of June’17 as the frequency had never gone beyond 48.50 Hz. 
(I) Status of Open Access applications during the month of June’2017
Status of Open Access Applications received and disposed by SLDC during the month was reviewed.

Deliberations in the meeting
Total 137 numbers of Short Term / Medium term and Collective transaction applications have been processed by SLDC for according Consent / NoC during the month. 
PART C – Issues likely to be discussed in the 135th OCC meeting of ERPC on 24.07.2017
C.1: Status of projects funded under PSDF schemes

In the PSDF review meeting held on 29.04.16 at New Delhi, it was advised to RPCs to monitor the status of all the projects funded by PSDF. Therefore, constituents are requested to update the status of projects which are being funded by PSDF in the desired format. 
The latest status as updated by OPTCL is as given below:
	Sl No


	Name of

Constituent
	Name of Project
	Date of approval from PSDF
	Target Date of Completion
	Amount

Approved (in Rs.)
	Amount

Drawn till date (in Rs.)
	Status as updated in
129th meeting

	3
	OPTCL
	Renovation & Up-gradation of protection and control systems of Sub-stations in the State of Odisha in order to rectify protection related deficiencies.
	11.05.15
	10.05.17
	162.5 Cr.


	25.16 Cr.
	Total contract awarded for

Rs. 51.35 Cr

Erection work  for received equipment is in progress.


C.2: Restoration of PLCC system of important lines

In 130th OCC meeting, OPTCL informed that PLCC panels at 220kV Joda end will be commissioned within a week. JUSNL informed that the Ramchandrapur end is ready in all respect for implementation of PLCC.

In 35th TCC, OPTCL informed that PLCC panels at 220kV Joda end will be commissioned by March 2017.

In 131st OCC, WBPDCL informed that shutdown was proposed on 31st March, 2017 to complete the work. OPTCL informed that PLCC panels will be commissioned by March 2017.

In the 107th PSOC meeting CGM (Telecom) stated that PLCC at Joda end will be commissioned on 27th March’2017.
In the 108th PSOC meeting, CGM (Telecom) stated that local test of PLCC was done. Since the line was under shutdown, remote test could not be taken up. After revival of the line towards 2nd week of May’2017, remote test will be done. 
In 110th PSOC meeting CGM (Telecom) stated that BPL is not responding to them. It was decided that CGM (Telecom) may intimate the same to ERPC.
Deliberations in the meeting

CGM (Telecom) stated that BPL had attended and commissioned the PLCC but some defects had been noticed in the Card. However, BPL has assured to replace the Card within 10 days.

[Action: CGM (Telecom)]

C.3: Status of construction of 400 kV Sterlite-Jharsuguda D/C sections

35th ERPC decided to extend the dead line for removal of LILO up to 15.04.2017 and advised Vedanta to strictly adhere to the schedule for commissioning of the dedicated line in all aspects.

Further, ERPC authorised CTU to open the LILO on 16.04.2017.

In 131st OCC, Vedanta submitted the item wise schedule. Subsequently, GRIDCO vide letter dated 13.04.17 has requested for extending the LILO connectivity till 30.06.2017.

In 132nd OCC, GRIDCO/OPTCL intimated that the line is expected to be completed by 31st May, 2017 in all respects. But keeping in view of peak summer the LILO may be allowed to continue till 30th June, 2017 to support the OPTCL system.

In view of above, OCC agreed to extend the interim LILO connectivity till 30th June, 2017. It was also decided that the LILO may be disconnected on 1st July, 2017.
GRIDCO/OPTCL assured that the dedicated line will be completed by mid of June, 2017 and the

LILO may be disconnected on 01.07.2017.

OCC advised OPTCL and Vedanta to complete the work at the earliest and no further extension will be granted for removal of LILO.
In 111th PSOC, Vedanta updated the latest status as follows:

	Activities
	Nos
	Status as updated in

35th TCC
	Status as updated in

133rd OCC
	Status as updated in

110th PSOC
	Remarks

	Tower Foundation
	64
	64
	64
	64
	Completed

	Tower Erection
	64
	59
	63
	64
	Completed

	Stringing /OPGW

Cabling & Testing
	20.5 km
	9 km completed
	15 km completed


	17.8
	

	Sub-station Bay
	2
	Bay construction completed
	Testing going on
	
	


Vedanta stated that they have targeted to complete all works by 02.08.2017. The line is expected to be charged by 12.08.2017.

[Action: Vedanta]
C.4: 220 kV inter-connecting lines of OPTCL with 400/220 kV Bolangir (PG), Keonjhar & Pandiabil S/s

PGCIL has already commissioned the 2x315MVA 400/220kV Bolangir S/s by LILOing of 400 kV Meramandali-Jeypore S/C line and 400/220 kV Keonjhar S/s with an objective of supplying power from ER grid to its adjoining areas in Odisha.

In 134th OCC of ERPC, SLDC deliberated the completion schedule of inter-connecting system as follows:

	Sl. 
	Name of the transmission line
	Completion schedule

	1.
	2 X 315MVA 400/220kV Bolangir S/s

	a.
	LILO of one circuit of Sadeipalli-Kesinga 220 kV D/C line at Bolangir S/S.
	Construction of 220 kV Sadeipali-Kesinga portion has started. Expected by Oct’17

	b.
	LILO of one circuit of Katapalli-Sadeipalli 220 kV D/C line at Bolangir S/S.
	Charged on 04.05.16

	2.
	400/220 kV Keonjhar S/S.

	a.
	Keonjhar (PG)-Keonjhar (220/33 kV) 220 kV D/C line
	Line is expected by Oct’2017

Keonjhar(220/33 kV) by Dec’17

	b.
	Keonjhar (PG)-Turumunga (220/133 kV) 220 kV D/C Line.
	By 2019

	3.
	400/220 kV Pandiabil Grid S/s

	a.
	Pratapsasan(OPTCL)-Pandiabil (PG) 220 kV D/C line
	December 2017 

	b.


	LILO of one circuit of Atri-Puri (Samangara) 220 kV D/C line at Pandiabil (PG). 
	Atri – Pandibili 220 kV one ckt charged on 19.05.2017

Pandiabili – Samangara 220 kV one ckt. charged on 20.05.17


In the last PSOC meeting, SLDC stated that permission for charging of 220 kV Pandiabili-Samangara line was allowed by ERLDC with an undertaking by SLDC to install RTU at Samangara within two months time. It was decided that Telecom may use the RTU already installed in any new S/S which is yet to be commissioned and install at Samangara S/S.  
Deliberations in the meeting
CGM (Telecom) stated that the RTU presently installed at Olaver S/S shall be removed and used at Samangara S/S by end of July’17. CGM (Const) has already been requested for provision of RTU at Samangara for booking the cost of the RTU.   

[Action: CGM (Const.) / CGM (Telecom.)] 

C.5: Preparation of crisis management plan for Cyber Security in Power Sector in line with CERT-IN.

The activity of the preparation of Crisis Management Plan for countering the cyber attacks and its implementation including the Mock Drills, audits etc. is being monitored by CEA regularly in line with crisis management plant of Ministry of Power. Power Utilities (including generation, transmission & distribution utilities) of eastern region are to furnish regularly, the updated status to Chief Engineer, Distribution Planning & Development Division, CEA. NTPC communicated their activity of the preparation of Crisis Management Plan for countering the cyber attacks vide letter dated 2nd August, 2013.

In 113th OCC, Member Secretary informed that during interaction with consultants of Grid Study Committee, NLDC agreed that they will plan for conducting workshops on crisis management plan for Cyber Security and few workshops will also be held in Eastern Region.

CESC vide letter dated 22.08.15 had furnished their status of the preparation of Crisis Management Plan (CMP) for Cyber attacks in their system.
In the 107th PSOC meeting, CGM (IT) informed that “Crisis management plan” work is awarded to M/s Digital Age Strategies Pvt. Ltd. The said firm has completed the study of Servers and Firewalls at SLDC, Bhubaneswar and back-up SLDC at Meramundali. Presently the data centers of SLDC and GRIDCO are being audited for IT security vulnerability assessment.

SLDC is requested to nominate one officer for attending the Cyber Security training to be held at Bengaluru during 11th to 15th April’2017. Nominations from GRIDCO and OPTCL have since been received. Top management awareness-cum Seminar on the subject shall be organized subsequently.

In the 108th PSOC meeting, IT stated that the Cyber Security training was held at Bengaluru during 11th to 15th April’2017. Regarding the proposed in house training to be held at Bangalore, members suggested to conduct the training at Bhubaneswar, so that all other officers can attend the same. IT requested to spare one room at SLDC building for Security Operation Center. SLDC stated that there is no spare room available at present.

In the 109th PSOC meeting CGM (IT) stated that top level sensitization program will be held on 25th May’17, after which the suggestions will be implemented.
In the 110th PSOC meeting, IT stated that the meeting was held on 23.06.2017. SLDC shall comply with the action to be taken relating to SCADA.

Deliberations in the meeting
DGM (Telecom) stated that the compliance of action to be taken on SCADA related issues is under process.
[Action: Telecom / (IT)]
C.6: Certification through BIS as per IS 18001:2007 to all generating / transmission units.

In 84th OCC meeting all constituents were requested to interact with BIS with intimation to ERPC and get certified as per CEA direction.

In 85th OCC, NTPC informed that NTPC-Farakka has been certified with IS 18001. Other constituents including OHPC requested to interact with BIS with intimation to ERPC and get certified as per CEA direction. The matter is getting reviewed by highest authorities with top priority.
In 104th OCC, WBPDCL informed that Bandel TPS is certified with IS 18001.

OPTCL vide letter No. TB-SO-MISC-9/2010/1914 dated 20.12.2014 had proposed to go for IS

18001:2007 certification as per direction of CEA.
In the 107th PSOC meeting O&M stated that the proposal will be placed before PSC due to single bid. 
In the 108th PSOC meeting, O&M stated that the bid has been cancelled. Negotiation with BIS is under process. 
In the 109th PSOC meeting Members suggested that O&M may contact OHPC to follow the procedure adopted by them.

In the 110th PSOC meeting CGM (O&M) stated that BIS office at Bhubaneswar was contacted in this regard. It was decided that OPTCL shall nominate its officers to take training. After completion of training they will conduct audit and certify.
Deliberations in the meeting

CGM (O&M) stated that 22 nos of officers are nominated from Chandaka, Mendhasal, Atri, Kesura, Bidanasi & Cuttack S/Ss to undergo training. Awareness training shall be started from 1st week of August’17. After receiving the price offer, order will be placed. 
[Action: CGM (O&M)]
C.7: Replacement of old RTU in Eastern Region for reporting of RTU / SAS to back-up control centre

The matter for replacement of old RTU in Eastern Region for reporting to back up control centre has been discussed in a special project review meeting held on 14th February 2017 at ERPC & also on 35th TCC/ERPC meeting held on 24th / 25th February 2017, It was also mentioned that there would not be any service support for the old RTUs from POWERGRID after 15 years of operation period. It was accordingly advised to ERLDC to form a committee with POWERGRID as a nodal agency for assessment of such old RTUs vis-a-vis further action plan on replacement.

It was also advised to submit a report in the next TCC/ERPC meeting.

The matter for replacement of old RTU in Eastern Region for reporting to back up control centre has been discussed again in 19th SCADA O&M meeting held at ERLDC, Kolkata on 07th April 2017, wherein nomination of nodal person name from OPTCL, WBSETCL, DVC, BSPTCL, JUSNL, POWERGRID ERTS-1, POWERGRID ERTS-2, ERLDC, MPL & Jorethang has been collected.

Nomination from NTPC all stations including Nabinagar, NHPC all stations, Dikchu, Teesta-III, Chuzachen, JITPL, GMR, Ind Bharat & APNRL are yet to be provided. ERLDC has already issued letter ref no: ERLDC / SCADA O&M / 2017/ dated 11.04.2017 for the same. It is requested to provide the nomination from these stations.
In the 108th PSOC meeting, CGM (Telecom) stated that tender has already been floated for replacement of old RTUs. A meeting is scheduled to be held between OPTCL, POWERGRID and Chemtrol during 1st week of May’17 to decide integration charges.  

In the 109th PSOC meeting, CGM (Telecom) stated that POWERGRID suggested to contact the vendor directly as the contract period is over. The tender has been cancelled. A fresh tender will be done.

In the 110th PSOC meeting, CGM (Telecom) stated that OPTCL has asked some clarifications regarding integration charges. After receiving the same, re-tendering process will be initiated.

Deliberations in the meeting

CGM (Telecom) stated that ERLDC has forwarded one RTU specification for Eastern region. A meeting is scheduled to be held on 04.08.2017 at ERLDC to finalize the tender specification. 
[Action: CGM (O&M) / CGM (Telecom)]
C.8: Implementation of Automatic Demand Management Scheme

OPTCL vide mail dated 24.02.2016 pointed that Hon’ble CERC vide their order dated 31.12.2015 passed in Sou-motu Petition No.- 5/SM/2014 in the matter of non-compliance of Regulation 5.4.2 (d) of IEGC directed all Respondents (SLDCs) for implantation of ADMS in their respective control area. CERC have allowed dead line till 30.06.2016 to the Respondent for implementation of ADMS. Failing which they will be liable for action under Section 142 of the Act.

   *****************************************************************************
The DPR for ADMS has already been approved by BoD, OPTCL. SLDC shall submit the proposal for funding by PSDF for ADMS to O&M wing of OPTCL for further action.
In the 108th PSOC meeting, SLDC stated that filling of format for PSDF and floating of tender is under process. The DPR will be sent to ERPC. CGM (Telecom) stated that SLDC may contact the consultant of PSDF for filling the format. The proposal has already been sent to NLDC to include for funding through PSDF.
In the 110th PSOC meeting, SLDC stated that floating of tender will be done within two weeks.
Deliberations in the meeting

SLDC stated that on implementation of GST in the country, the commercial aspect of the tender need to be changed. The tender is expected to be floated within 10 days.
[Action: SLDC]
C.9: Pollution mapping for Eastern Region
Powergrid updated the latest status as follows: 

	
	No of locations
	Installed locations
	1st set of measurements
	2nd set of measurements
	3rd set of measurements
	4th set of measurements
	5th set of measurements

	OPTCL
	164
	102
	100
	90
	79
	78
	24


Powergrid added that they prepared an online format to submit the details of measurements.

Powergrid requested to fill the Google form (https://goo.gl/6375HJ) for onward submission of measurements for better analysis of results.

Further, the schedule for measurement as informed vide letter dated 20.01.2016 & mail dated 21.01.2016 are as follows:

Measurement Schedule

	4th set
	5th set
	6th set

	21st -30th Sep 2016
	21st -31st Jan 2017
	21st -31st May 2017


OCC advised all the constituents to complete the measurements as per the schedule.

It is also requested to send the onward measurement results to following emails in addition to current email ids

1. vbhaskar@powergridindia.com  2. ritesh.kumar@powergridindia.com

In the 110th PSOC meeting, O&M stated that data for 92 locations have been collected.

Deliberations in the meeting
As reported by O&M to POWERGRID, for 6th phase measurement, data from 54 Nos of locations are available during the month of June’17. Due to continuous rain, further testing has been stalled as the data so obtained will not be so much useful.
[Action: CGM (O&M)]
C.10: Mock Black start exercises in Eastern Region 

The tentative schedule of black-start exercises for F.Y 2017-18 given by OCC is as follows
	Sl. No.
	Name of Hydro Station
	Schedule
	Tentative Date
	Schedule
	Tentative Date

	
	
	Test-I
	
	Test-II
	

	1
	Upper Kolab
	Last week of May-2017
	Conducted on 30th May 2017
	Last week of January 2018
	

	3
	Rengali
	2nd week of June 2017
	To be conducted on 29.06.17
	Last week of November 2017
	

	4
	U. Indravati
	3rd week of June 2017
	2nd week of July-2017
	2nd week of February 2018
	

	6
	Balimela
	3rd week of October  2017
	
	1st week of March 2018
	

	9
	Burla
	Last week of June 2017
	Can be conducted after synchronization of #2
	Last week of February 2018
	


In the 110th PSOC meeting, SLDC suggested that OHPC may send their officers of different Power Stations to SLDC to study and realize the conditions of frequent increase / decrease of hydro generation instruction given by SLDC on real time operation. 
Deliberations in the meeting
SLDC stated that OHPC may intimate their readiness for conducting mock black start exercise for Burla HEP, as unit #2 has been synchronized. Mock black start exercise for Indravati HEP could not be conducted due to tower collapse of Indravati-Theruvali ckt 3&4. 
[Action: OHPC / SLDC]
PART-D – Operational Issues
D.1: Non-compliance of drawal schedule by DISCOMs

Non compliance of drawal schedule messages issued to Discoms during the month of June’17:
	Sl. No
	Name of Discom
	No. of message issued
	Over drawal (MU)
	Deviation (%)

	1
	CESU
	6
	4.408
	0.587

	2
	WESCO
	7
	-2.890
	0.518

	3
	NESCO
	9
	4.437
	1.02

	4
	SOUTHCO
	0
	-3.932
	1.40

	
	Total
	22
	2.023
	


It is noticed that all the Distribution Utilities except NESCO had overdrawn substantial quantum.
Deliberations in the meeting

It is noticed that CESU has overdrawn 4.408 MU followed by NESCO 4.437 MU, while NESCO & SOUTHCO were under drawn during the month. All Distribution Utilities were advised to predict their day ahead drawal accurately to avoid deviation. SLDC stated that all the executives of Discoms involved in drawal scheduling activity should be well conversant with the Regulations and procedures. 

[Action: SLDC / Discoms]   

D.2: Prolonged outage of transmission elements and tentative revival dates
 The tentative revival dates of transmission elements are updated in the last meeting are as follows:

	  Sl.No
	Name of transmission element
	Reason of outage
	Probable date of revival

	1
	220/132 kV, 100 MVA, Auto- 2 at Duburi.
	Oil leakage since 24th October’2016
	July’2017

	2.
	220/132kV, 100MVA  Auto-2 & 3 at Bhadrak
	Fire hazard on 31.05.2017
	Auto Tfr is yet to be reached at site

	3
	400kV Meramundali-Vedanta ckt.-I & II
	3 nos of tower collapsed on 11.06.17
	15th August’2017


[Action: Vedanta / CGM (Const.)]
D.3: Communication issues 
Installation of communication equipment by CGPs / IPP /  Industries.
The status of data communication from CGPs as deliberated in the last meeting is as follows.

	Sl.
	Name of CGP
	Present status

	1
	M/s IFFCO, Paradeep
	Outdoor commissioning work completed. RTU was locally tested. CVT already replaced. Data will be integrated after restoration of OPGW between New Duburi & Paradeep.

	2
	M/s MSP Mettalicks
	PLCC / RTU installed. Database has already been prepared by OPTCL. Final RTU integration with OPTCL system by the vendor is awaited.

	3
	M/s NINL, Duburi
	M/s NINL has requested for Scheme, BOQ for PLCC/SCADA, which has been forwarded by OPTCL. No action has been taken by NINL so far. 

	4
	M/s Rohit Ferrotech
	PLCC established and inspection by Telecom Engineers completed.  Database has already been prepared by OPTCL.    

	5
	CONCAST
	No kV/Hz. (Industry is under lock up)

	6
	VISA
	CB & Status data are not available

	7
	Paradeep
	Data not available at ERLDC (Transducers need replacement)

	8
	Vedanta (400kV) 
	Frequent interruption of Line data & Generation data 

	9
	GMR
	GMR line data not available as reported by ERLDC.

	10
	Samangar & Lapanga
	No data available as reported by ERLDC

	11
	NALCO
	No data available since 14.07.17. NALCO is not responding


GCC has convened a meeting with all the CGP and EHT consumers on 21st February’2017 to discuss the communication issues. In the 106th PSOC, SGM (Telecom) stated that data from Paradeep S/S will be obtained after availing shutdown of 220 kV Duburi-Paradeep DC line for OPGW stringing. 

In the 107th PSOC meeting, GCC stated that the CGPs and EHT consumers have assured to establish communication system within a specified time limit. In case they fail to do so the matter will be placed before the OERC.

In the 108th PSOC meeting, GCC stated that, the minutes of the meeting have already been forwarded to OERC. SLDC stated that the generation of GMR unit connected to the State network is being received. It was decided that CGM (Telecom) will write to GMR for installation of a separate RTU for the said unit.
In the 109th PSOC meeting, Members suggested that GCC may file a Petition before the OERC for non compliance of data communication by the CGPs.
In the 110th PSOC meeting, GCC stated that OERC has asked the present status of data communication, which will be submitted.
 Deliberations in the meeting

GCC stated that the information has been received from Telecom. The status shall be submitted to OERC.
[Action: GCC / Telecom]

D.4: Web based drawal / generation scheduling.

In the 107th PSOC meeting, CGM (IT) informed that Generators web based scheduling work is completed except for generation of report indicating “Final Generation Schedule” for which SLDC shall furnish the requisite format.  SLDC was requested for a report to ascertain the submission of schedule by the CGPs.

It was decided to take a backup of the past web scheduling submissions by the generators and preserve them off line.

It is proposed to Go-Live for Generators web based scheduling w.e.f 1st April’2017. SLDC may issue necessary order.

Due to non-availability of sorting function for Date & Name of CGP under Accept / Edit Generator DC, difficulty is being faced by SLDC to find out the data of a particular CGP for a particular date. Further, the link for final schedule preparation has not been updated in the Web Based Scheduling application. Further, it is suggested by SLDC to take suitable back up of all the old records i.e. the DCs sent by the CGPs previously and clean the application database up to 31st   March 2017.
In the 108th PSOC meeting, IT stated that final report generation will be completed by April’2017. Searching and Sorting of data has been done. The status to indicate whether the CGP has done scheduling or not, will be completed. SLDC may go for parallel run of the program for the month of May and June’17. From 1st July’17 the software will be made operative. SLDC may write a letter in line with the above program.
In the 109th PSOC meeting, it was decided that acceptance of schedule for the month of April will be done by SLDC. A meeting will be conducted with IT and the scheduling group on 30th May’17 to resolve the pending issues.

In the 110th PSOC meeting, IT stated that the requirement of SLDC has already been done. It was decided in the meeting that from 1st July’17 the web based scheduling will be run parallel with the conventional scheduling format. From 1st August’17 only web based scheduling will be considered. All CGPs may be intimated accordingly by SLDC.
Deliberations in the meeting
It was decided that from 1st August 2017 the schedule submitted through web portal will be considered. The web based schedule will be implemented for TTPS and Ib TPS from 1st September’2017. SLDC may intimate all the CGP and State Thermal generators accordingly.

[Action: SLDC]
D.5: Implementation of Automatic Meter Reading for OPTCL-Discom interface points.

The work for Automatic Meter Reading (AMR) for all the interface points is in progress. 

It was deliberated that that from 1st March onwards the AMR shall be made “Go live”. Data will be available after one hour lapses of time.

In the 100th PSOC meeting CGM (IT) stated that by end of August’2016 testing of all meters of CESU control area will be completed for billing purpose. SLDC may check August data from both the meters.

In the 104th PSOC meeting, DGM (IT) stated that, data from 90 Nos of S/Ss will be provided by January’2017. Gridco stated that the events such as PT failure, CT polarity reversal, meter power failure, MD reset, time synchronization etc. are not being incorporated the AMR. It was decided that IT, SLDC and GRIDCO may have a separate meeting to resolve the issue.
In the 105th PSOC meeting DGM (IT) stated that, data from 100 Nos of S/Ss will be provided by February’17. The issues raised by Gridco will be addressed except Time synchronization and MD reset.

In the 107th PSOC meeting, CGM (IT) stated that AMI-UAT open points viz., (a) “Status Flag” for events and (b) Phaser Diagram issues are resolved by TCS. SLDC and GRIDCO were requested to spare their officers on 24th and 25th March’17 for a final testing and Sign-off. Further if any non-fatal cosmetic issues remain, the same shall be resolved by TCS during support service period. Accordingly, an undertaking shall be obtained by IT from TCS. Hence it is proposed to go for parallel run with effect from 1st April’2017 for a period of six months after testing the software by the UAT team, before going Live. Out of 125 Grid S/Ss, 101 S/Ss reported 100 % data during March 2017.

In the 108th PSOC meeting IT stated that data for 39 Nos out of 41 Nos of CESU interface S/Ss have been completed. SLDC may prepare bill from 1st July with both from AMR and legacy meter data. If there is no difference between both the bills, the software will be made Go Live. It was further decided that AMR data will be taken on 1st day and manual data will be taken on 2nd day.   

In the 109th PSOC meeting IT stated that parallel billing for 188 Nos of metering points has been done but the report is yet to be received by IT. UAT team have given their observations. The parallel billing shall be continued. 

Deliberations in the meeting

DGM (IT) stated that TCS will comply with the discrepancies identified by UAT team by 20th August’17. Director (Commercial) will take a meeting on 27th August’17. The no of decimal points to be kept will be decided in the meeting.

 [Action: SLDC / IT]

D.6: Software for Deviation charge billing.

Hon’ble OERC may notify “Intra State Deviation settlement and related matters” Regulation at any time. For implementation of the regulation, required software for Deviation Charge billing need to be developed and tested. CGM (IT) may take necessary steps for development of the software.

In the 106th PSOC meeting CGM (IT) stated that the work will be awarded to TCS after notification of Deviation Mechanism Regulations by OERC. SLDC stated that OERC may not allow time for implementation of the DSM Regulations. As such action may be taken for placing Order.

In the 107th PSOC meeting, SLDC stated that IT may take necessary steps for placing order for the DSM software.

In the 109th PSOC meeting, IT stated that TCS will forward their commercial offer by 1st week of June’17.
In the 110th PSOC meeting, IT stated that the DCU (Data Concentration Unit) installed at Rengali PH panel has been removed. OHPC may enquire over the matter. 

The list of discrepancy identified by UAT team shall be forwarded to TCS for rectification.
Deliberations in the meeting

IT stated that TCS is reluctant to forward their offer till resolve of AMR issue. Members stated that there is no relation between the two issues. IT may go for tendering for development of the software.

 [Action: (IT) / SLDC] 

D.7.DISCOM Issues

CESU

1. Wide mismatch between actual drawal data and drawal displayed in the SCADA. The mismatch is to the tune of -105 to +221 MW some times. Action may be taken to reduce the mismatch.

2. Budhapal 33 kV feeder emanating from Rengali 220/132 kV S/S is now fully dedicated to supply power to WESCO. SLDC is requested to incorporate the above feeder in WESCO’s Energy Accounting and deduct from CESU drawal. OPTCL may provide metering infrastructure if not available.

3. Arrears payable by WESCO & NESCO to CESU to the tune of 12.2183 Crore & 6.2182 Crore respectively may be resolved.

Deliberations in the meeting

SLDC stated that CESU may develop the demand estimation logic without depending fully on SCADA data. The SCADA display data is for monitoring purpose only, which may not match exactly with the meter data. Both data may be compared to ascertain the error correction factor. 
It was decided that OPTCL will provide energy meter for Budhapal 33 kV feeder at Rengali S/S. SLDC will prepare the energy accounting for WESCO and CESU considering the meter data. 

CESU may resolve the arrear payable by WESCO & NESCO mutually.

[Action: CESU / NESCO/OPTCL/WESCO]

PART E: OPERATIONAL PLANNING
E.1:  Commissioning status of new Transmission elements. 
The status of commissioning of new transmission elements deliberated in the meeting is as follows:
	   Sl. No
	Transmission element details
	Present Status

	1
	Commissioning of 220 kV Jayanagar-Jeypore 2nd DC line 
	Work has already been started. Expected to be completed by December’ 2017.

	2
	Commissioning of 400 kV Meramundali-Mendhasal 2nd ckt.
	Line is ready and shall be charged after commissioning of 3rd ICT at Mendhasal, which is under progress. Expected by December’2017.

	3
	Commissioning of 132 kV Baripada (PG)-Jaleswar line
	Work has already been started, which will be completed by July 2017. 

	4
	Commissioning of 220/132 kV Kesinga S/S
	Work under progress. Expected by December’ 2017.


The list of Grid S/Ss already charged earlier and scheduled to be charged during FY 2017-18 has been placed in the 109th meeting. The Discoms were requested to take necessary action for availing power supply from those S/Ss and prepare their action plan for takeoff arrangement. 
[Action: CGM (Const) / All DISCOMs]
E.2: PMU Installation at Indravati & Balimela by Powergrid

Power supply to PMUs to be commissioned by Powergrid at Indravati PH & Balimela PH, needs to be extended by OHPC authorities.

Deliberations in the meeting

POWERGRID stated that PMUs will be installed in the State at TTPS, Budhipadar, TSTPP & Monnet, Balimela PH and Indravati PH locations. It was decided that OHPC corporate office shall write a letter for Balimela and Indravati HEP to extend DC supply to the PMU at their respective Stations. Powergrid may take follow up action. Shutdown for connectivity if required shall be arranged by O&M. 
[Action: OHPC/ CGM (Telecom) / POWERGRID/SLDC]
E.3: Installation of ABT compliance Energy Meter at Ib TPS feeders & Generators / Furnishing of DC

SLDC shall prepare the schedule and Energy Accounting in respect of IbTPS. It is learnt that the Main meter installed by IbTPS feeders is recording 30 minutes reading while Check meter provided by OPTCL is recording 15 minutes reading. Unless ABT compliance Main and Check energy meters installed in IbTPS feeders & Generators, the energy accounting and PAFM cannot be computed. It is requested OPTCL / IbTPS to provide ABT compliance Main and Check meters in all the 220 kV IbTPS feeders & Generators.

In the last meeting, O&M stated that IB TPS has placed requisition for 6 Nos of Apex meters. SLDC stated that for replacement of all meters including generators, 10 nos of meters will be required. IBTPS may place their requisition for 10 Nos. of meters.

Deliberations in the meeting

IBTPS may place their requisition for 10 Nos. of meters.  

[Action: OPTCL / IB TPS]    

E.4: Major Events in the month of June’17
07.06.17: 132/33kV, 40 MVA tfr has been replaced by 63 MVA tfr at Ransinghpur sub-station.

23.06.17: 132kV Khajuriakata-Aarti Steel ckt. made LILO at Nuapatana sub-station

[Members may note]
E.5: Important Grid Incidences during the month of June’17.
There was only two Grid incidents occurred during the month. 
Deliberations in the meeting
O&M may analyze the incident for deliberation in the OCC meeting of ERPC. 

[Action: O&M / SLDC]

E.6: Outage of major transmission Elements during the month of June’17. (above 10 hrs).
Outage of major transmission elements above 10 hours during the month was reviewed. The outages are due to jumper snapping and insulator damage.

[Action: O&M]

E.8:  Review of Outage Program of State Generators / Transmission elements for the month of Aug’17:
Tentative Outage programme for State Generators for the month of August’2017 are as follows:
	Sl.
	Station
	Unit
	Period
	Remarks

	1
	Burla
	# 5

# 6

# 7
	25.10.16 to continue

16.10.15 to continue

21.02.17 to 22.08.17
	Under R,M & U

Under R, M & U

GT problem

	2
	Chiplima
	# 1

# 3
	15.04.17 to 28.07.17

15.10.15 to continue
	Annual Maintenance & bush replacement

Under R,M & U

	3
	Balimela
	# 1

# 7
	05.08.16 to continue

16.04.17 to 22.08.17
	Under R,M & U

Generator Stator problem

	4
	Rengali
	# 5
	21.03.17 to 16.08.17
	Hoist gate problem

	5
	Upper Kolab
	# 2

# 3
	28.05.17 to 15.08.17

19.04.17 to 31.08.17
	MIV Problem

Forced outage due to stator fault


E.9: Generation Program for the month of August’17.
Generation schedule for the month of August’17 furnished by OHPC are given below. 

	Name of Hydro Gen. Station               
	Generation Program (MW)
	Reservoir Level as on 01.07.16
	Reservoir Level as on 01.07.17
	MDDL
	High Flood    Reservoir Level

	
	August’17

(1st fortnight)
	August’17

(2nd fortnight)
	
	
	
	

	HPS-I, Burla
	130
	130
	597.06 ft 
	 598.52 ft
	590 ft.
	630 ft.

	HPS-II, Chipilima
	40
	40
	-
	-
	-
	-

	Balimela
	270
	270
	1477.40 ft 
	1458.30 ft
	1440 ft.
	1516 ft.

	Rengali
	150
	150
	110.01 mt

1.78mt mtr mt
	110.25 mt mt
	109.72mtr 
	123.5 mtr.

	U.Kolab
	160
	160
	848.39 mt mt
	848.47 mt
	844 mtr 
	858 mtr.

	U. Indravati
	300
	300
	630.39 mt
	628.94mt mt
	625mtr 
	642 mtr

	MKD (O/D)
	40
	40
	2713.00 ft 
	2707.80 ft
	2685 ft.
	2750 ft.

	TOTAL
	1090
	1090
	
	
	
	


Generation schedule may change depending on inflow & availability of machine.

E.10: Compliance of CEA Regulations for Grid Connectivity of Renewable Energy Sources.
As per CEA (Technical Standards for connectivity to Grid) Regulations, 2007, dated 21st February 2007, the pertinent clauses 6 (iii) & 6 (iv) (b) of general Connectivity Conditions shall be applicable to all the Generating Projects including the renewable, which are getting connected to the Grid at voltage level of 33kV & above. Subsequently, CEA have notified the CEA (Technical Standards for Connectivity of the Distributed Generation Resources) Regulations 2013 dated 30.09.2013. These Regulations are applicable for “Distributed Generation Resources”, which means a Generating Station feeding electricity into the System at voltage level below 33kV. Needless to mention that these Regulations also cover the renewable projects connected to the Distribution Licensee’s System at voltage level of below 33kV. The letter received from CEA is annexed herewith. 

All the Distribution / Transmission Licensee may please indicate the status in this regard and the action plan with definite time frame to ensure real time data telemetry from all the grid connected renewable Generators / Plants to SLDC.

SLDC has already forwarded the Regulations & a letter received from DoE, Govt. of Odisha to the Distribution Licensees.  

In the 110th PSOC meeting CGM (PP) stated that Gridco have already contacted the RE generators. However a meeting will be convened soon to decide the strategy.

Deliberations in the meeting
CGM (PP) stated that a meeting with all RE generator, Telecom & SLDC is scheduled to be held on 27.07.2017 to discuss the issue.

[Action: GRIDCO]
E.11: Anticipated power generation and demand for the month of August’2017.
	Sl. No
	Discom
	Average
	Peak

	1
	CESU
	950
	1200

	2
	WESCO
	900
	1050

	3
	NESCO
	700
	980

	4
	SOUTHCO
	400
	450

	6
	Total Discom
	2950
	3680

	
	System Loss
	150
	200

	
	Total Demand
	3200
	3880

	Availability
	
	

	1
	Hydro
	1090
	1200

	2
	State Thermal
	750
	750

	3
	IPP, small hydro &RE
	550
	850

	4
	ISGS share (including OA)
	900
	1000

	5
	CGP support (OA)
	200
	200

	6
	Total availability
	3400
	4000

	7
	Surplus / Deficit
	200
	120


PART F: OTHER ISSUES

All members expressed their gratitude to Er A.K.Mishra, Director (Operation), OHPC, who is going to retire from service on superannuation by end of this month for his guidance and advice. PSOC will remember his valuable advices and the foot prints he has left for all times with deep regard.  

F.1. TTPS Issue
TTPS proposed for shutdown of # 6 from 24th July to 29th July’2017 to inspect the vibration and temperature rise and shutdown of # 5 for boiler license renewal. 

Deliberations in the meeting

SLDC may examine and take necessary steps to issue shutdown of # 5 in consultation with GRIDCO.

[Action: SLDC/ GRIDCO]
F.2. Testing of Hydro potential 

CEA has directed all SLDC to ask all hydro stations to generate up to the capacity everyday at least for 30 minutes to ascertain the hydro potential available in the country. SLDC shall write a letter to all hydro stations accordingly.

[Action: SLDC / OHPC]   

F.3:  Date and Venue of the next (112th) PSOC meeting.
ANNEXURE

[image: image2.png]* 114th Power System Operational Co-ordination Committee Meeting
' : [ At 11:00 A.M. on 19.07.2017]
. : [At PTC, Chandaka]

E-mail Address

4

W
s
©
3 < ®
¢
i i

=) P-38

Ne.|

érévM(‘Ps) %3%0???3
B
con@ay| orree | perralg
CGMZRHC) 9432907019
2
&
=

QY9903 - 1@G 4 0 i1y :

-bpmish
ele F é Zglga-m

Rdil

K, Samasduass, |£4Lr0 | OPTeL | 438907930
9D el o] 943890781 |Sam oo L&Y

:

y DaM NTPC/TTes | 9437966690

A k. Rorad | puni(l] 5P7¢ |ays59omy3 |l T o\
PO P oo Frossrin ey 3 So
M.K. Panda FHH4CE 222 m‘mc M
e e NZh | 16465 74 587 ’m
By o [wverer [wesco Javaniserg

' D G )| Telecery.| a4
Gl Bzl Dl i N80Tyl | L skmice |
Sk M BPTL [828s34202y
D438 90209¢ R

[

; &E‘ "

A
pio,
=
%
N
*
N
™
ii
®)
%
Q
K
Q
bo
J
b,
3
o~
‘%
)
Q

kS

¢
o2

S

‘
14
£

o
)
|
\\
NG
\§
\
{
9,0
v
O
30
d
8
(N

> [
= I
E‘@
y:
E
%
9
h
?7

=
g
~<

L

bt i — — et = o Yt
i
)

EE
5

|

!

FX
T

3 |2

® |3

49
d

3

3

&

g

§

o
%Iﬁ

S
~
Y
.
&
>
v

il

<
3

S5

&

? 2

S

3

R o

:

\C

Q

‘j' N

)

b

IQ
\Y)
N

7 o | Ay ) e pystsed5o [ece T | G
P pd | Gmoth| Cav (A4t psels |G e,
hle. Lok |6n(008] We6 | 34309040 2 prePn@necs
B D ) Mndne [Aum  |(WeLeo (29329060 F |rasenabt@gmaillds K onvag

—
|8
U

D

el T




[image: image3.png]N
o

) W A~ w - = ;
B
S

Phoming A v | OMEC
P o oA e Sl o v DTS
A ‘

E=
[\ |
\

7’

-
‘k

)

™
K/
\
I

Z

e T
IERRTE
ETnR 73

W [9%]
N [\S)
v >
>
> A w|>
iy . - 0=
EENE §
' Y
A}
o =
: !
%3
—
[N &)
S 2
(2l
sy
Ay
Vs
So
~9
S
<
‘\)
‘ , D

NV

!

y

&
Q .
HI§§

-
[Ta

'g F
O

=

¢

N

ol |

>

[\

3

G

A

ol

&

il

[aay





