[image: image1.emf]
Distribution list

1. The Director (Commercial), Gridco, Bhubaneswar

2. The Director (Operation), OPTCL, Bhubaneswar

3. The Director (Projects), OPTCL, Bhubaneswar

4. The Director (Operation), OHPC, Bhubaneswar

5. The CGM (O&M), OPTCL, Bhubaneswar.

6. The CGM (Const.), OPTCL Bhubaneswar.

7. The CGM (RT&C), OPTCL, Bhubaneswar.

8. The CGM (PP), GRIDCO, Bhubaneswar.

9. The CGM (IT), OPTCL, Bhubaneswar.

10. The CGM (Telecom), OPTCL, Bhubaneswar.

11. The Sr. G.M (Const)-I, OPTCL, Bhubaneswar.

12. The Sr. G.M (Const)-II, OPTCL, Sambalpur.

13. The Sr. G.M (CPC), OPTCL, Bhubaneswar.

14. The Sr. G.M (CP), OPTCL, Bhubaneswar.

15. The Sr. G.M. (O&M), Zone-I, Narendrapur 

16. The Sr. G.M.(O&M), Zone-II, Meramundali.

17. The CEO, CESU, Bhubaneswar.

18. The A.O., WESCO, Burla

19. The A.O., NESCO, Balasore

20. The A.O., SOUTHCO, Berhampur.

21. The Member Secretary (GCC), OPTCL.

22. The ED, Power Grid Corporation of India, Bhubaneswar.

23. The Sr. G.M. (El.), BHEP, Balimela

24. The A.G.M. (El.), CHEP, Chiplima

25. The Sr. G.M. (El.), UIHEP, Mukhiguda

26. The Sr. G.M. (El.), RHEP, Rengali

27. The D.G.M. (El.), HHEP, Burla

28. The D.G.M. (El.), UKHEP, Bariniput, Koraput

29. The S.E. (O&M), Machhakund

30. The DGM (Elect.), IbTPS, OPGC, Banharpali.

31. The Vice President (O), IMFA, Choudwar.

32. The D.G.M. (O&M), NTPC (TTPS), Talcher.

33. The AGM (Elect.), JINDAL Stainless Ltd., Duburi

34. The G.M, HINDALCO, Hirakud.

35. The G.M.CPP, NALCO, Angul.

36. The Director, M/s. Jindal Steel & Power Ltd., Angul

37. The AVP-Vedanta Ltd (IPP), Jharsuguda

38. The G.M, Vedanta Ltd (CGP), Jharsuguda.

39. The DGM (Power Distribution), RSP, Rourkela.

40. Joint President, Aditya Aluminium Ltd., Lapanga, Sambalpur

41. The G.M. (Elect.),  Bhusan Steel Limited. Meramundali

42. The G.M. (Elect.), Bhusan Power & Steel Ltd, Budhipadar.
43. The G.M. (Elect.), IFFCO Limited.

44. Director & COO, GMR Kamalanga Energy Limited, Satyanagar, Bhubaneswar.

45. The CEO, Bhubaneswar Power Pvt. Ltd, IRC Village, Nayapalli, Bhubaneswar.

46. M/S Tata Power & Steel Ltd., Kalinganagar

Odisha Power Transmission Corporation Ltd. Bhubaneswar.


Minutes of 118th PSOC meeting held on 26.02.2018 at PTC, Chandaka, BBSR
List of participants is at Annexure.

CGM, SLDC welcomed all the members to the 118th PSOC meeting. In his welcome address, he highlighted the system performance for the month of January’2018 and overall power scenario of the State. He also emphasized on the power drawal, made by all the Discoms during the month. 
D.G.M. (SS), SLDC took the agenda items for discussion.
The review proceeded as follows: 
1: Confirmation of minutes of 117th PSOC meeting held on 27.01.2017
The minutes of meeting was circulated vide letter No. SGM (PS)-PL-15/2016/435(47) dated 05.02.2018 to all the members and also uploaded in the SLDC website. No comment has been received from any of the members.

Deliberation in the meeting:
The minutes of 117th PSOC meeting was confirmed. 
PART B : SYSTEM PERFORMANCE
B1: Review of Grid Performance for the month of January’2018.
(A)  Frequency 

It was noticed that, during the month of January’18, 76.51 % of times the frequency remained in the IEGC band i.e.  49.90Hz - 50.05Hz in comparison to 72.78 % during the month of  December’17. The maximum and minimum System frequency during the month was 50.16 Hz & 49.74 Hz respectively.
Deliberations in the meeting
SLDC stated that the frequency obtained by Telecom is differing marginally from ERLDC frequency. Telecom stated that the point from which frequency collected by them are different from that of ERLDC. 
 (B)  Grid demand 

Grid demand for the month of  January’18 was reviewed. The average consumption during the month was 3107 MW. The maximum System demand of 4251 MW occurred on 28.01.18 at 20:00 Hrs and minimum demand of 2244 MW occurred on 04.01.18 at 04:00 Hrs. 
Deliberation in the meeting

It is observed that the average demand during the month of  January’ 18 has been increased by 188 MW while the peak demand  was increased by 21 MW from that of December’17. The average demand during the month has been increased by 287 MW in comparison to January’17. Due to load growth and import of power by M/s Vedanta Ltd. through Open Access transaction are the reasons for increase of average demand.
 (C)  Voltage Profile of important Sub Stations in OPTCL System during the month of Jan’18.

The Voltage profile at different 220 kV buses in OPTCL system during the month of January’18 was reviewed. 
The maximum Voltage of 240.00 kV occurred at Jayanagar 220 kV bus. Katapali 220 kV bus has experienced the minimum Voltage of 206.33 kV. The 220 kV Voltage profile of Jayanagar & Narendrapur and 400 kV Voltage profile of Meramundali  & New Duburi bus during the month of January 2017 in 15 minute block was reviewed.
Deliberation in the meeting:
Members opined that installation of bus reactor at Meramundali need to be explored. Further it was decided that SLDC shall monitor the VAR injection by JSPL & BSL on real time basis and issue instruction to absorb VAr at high voltage condition failing which one ckt. of the above industries shall be disconnected from both the ends. 







 [Action: O&M / JSPL / BSL / SLDC]
(D) Loading of 220/ 132 kV Auto at 220 kV S/Ss in OPTCL system for the month of January’18.

Auto loading of all 220 kV S/Ss was reviewed. 
(E) DISCOM Drawal during the month of January’18 
The schedule and actual energy drawal by Discoms for the month of January’18 was reviewed. 
Deliberation in the meeting:
It was noticed that the total energy drawal by CESU during the month was 2.615 MU above the schedule, while NESCO had under drawn 5.017 MU. SOUTHCO & WESCO drawal were in line with the scheduled energy. CESU stated that the logic of energy accounting should be intimated to them. SLDC stated that CESU may discuss with the Energy accounting cell of SLDC in this regard. CESU has agreed to the proposal.

 [Action: CESU /SLDC] 
(F) Energy Generation / import during the month of January’18 
Energy generation and exchange during the month of January’18 was reviewed. The total quantum of energy drawn from all the generation sources including Central Sector Share and CGP/IPP support during the month was 2311.40 MU. 
Deliberations in the meeting
The energy demand has been increased due to import of power by M/S Vedanta Ltd. through Open Access transaction. 
 (G) Drawal of Machhakund Power during the month of January’18
The drawal of Machhakund power during the month of January’18 was 19.62 MU, against AP drawal of 17.395 MU. 
Deliberations in the meeting

OPTCL stated that although 132/33 kV Podagada S/S has been commissioned on 09.02.2018 SOUTHCO is yet to make takeoff arrangement for drawal of power. SOUTHCO stated that about construction of 1.5 Kms of 33 kV line is required, which is being held up for shortage of fund. Members opined that O&M may insist to include this line for funding through in Dindayal village electrification scheme. SOUTHCO may discuss with O&M in this regard. 
[Action; O&M / SOUTHCO]

(H) Under Frequency relay operation in OPTCL System during the month of January’18.

There is no UF Relay operation during the month of January’18 as the frequency had never gone beyond 48.50 Hz. 
(I) Status of Open Access applications during the month of January’2018
Status of Open Access Applications received and disposed by SLDC during the month was reviewed.

Deliberations in the meeting
Total 135 numbers of Short Term / Medium term and Collective transaction applications have been processed by SLDC for according Approval / Consent / NoC during the month. 
PART C – Issues discussed in the 142nd  OCC meeting of ERPC on 23.02.2018

C.1: Status of projects funded under PSDF schemes

In the PSDF review meeting, it was advised to RPCs to monitor the status of all the projects funded by PSDF. Therefore, constituents are requested to update the status of projects which are being funded by PSDF in the desired format.

The latest status as updated by OPTCL / OHPC is as given below:
	Sl No


	Name of

Constituent
	Name of Project
	Date of approval from PSDF
	Target Date of Completion
	PSDF grant
Approved (in Rs.)
	Amount

Drawn till date (in Rs.)
	Status as updated in
129th meeting

	4
	OPTCL
	Renovation & Up-gradation of protection and control systems of Sub-stations in the State of Odisha in order to rectify protection related deficiencies.
	10.05.15
	10.05.17
	162.5 Cr.


	25.16 Cr.
	Total contract awarded for

Rs. 51.35 Cr



	13
	OHPC
	Renovation & up-gradation of protection & control system of 4 nos. OHPC sub-stations
	
	U.Kolab-

March 19

Balimela-

Feb 2019

U.Indravati-

Jan 19

Burla-Nov

2018,

Chiplima

Dec 2018
	22.35 Cr.
	
	Tendering under process


In the 116th PSOC meeting, OPTCL stated that they are linking another project for funding through PSDF and the target date will be changed. The revised target date for completion will be intimated to ERPC. Further, technical specification for 400 kV bus reactors at Meramundali S/S is yet to be prepared. It was suggested that CPC may expedite the same.

In the 117th PSOC meeting O&M deliberated that 400 kV bus Reactor for Meramundali S/S shall be procured after getting sanction by PSDF. 
Deliberations in the meeting

SLDC stated that ADMS for SLDC is to be incorporated as PSDF funding item. O&M shall intimate ERPC the revised target date.  
[Action: CGM (O&M) / SLDC]

C.2: PPA details for the years 2017-18 to 2019-20
CEA vide mail dated 21st November 2017 informed that it has been decided to estimate the demand and availability of power (energy and peak), initially for the year 2017-18 and subsequently for the years 2018-19 and 2019-20. In this regard, PPA details for the years 2017- 18 to 2019-20 are required as per the format available in the ERPC agenda.
All the constituents furnish the data as per the format to CEA by email: rk.jena@gov.in.
In the 117th PSOC meeting, CGM (PP) stated that GRIDCO is preparing the details of PPA made by them. GMR was requested to forward the required data.

Deliberations in the meeting

CGM (PP) stated that GRIDCO will forward the required information to ERPC by the end of February’2018.       
[Action: GRIDCO / GMR / OPGC]
C.3: 220 kV inter-connecting lines of OPTCL with 400/220 kV Bolangir (PG), Keonjhar & Pandiabil S/s
PGCIL has already commissioned the 2 X 315MVA 400/220kV Bolangir S/s by LILOing of 400 kV Meramandali-Jeypore S/C line and 400/220 kV Keonjhar S/s with an objective of supplying power from ER grid to its adjoining areas in Odisha.
In 118th PSOC meeting the status has been updated as follows:
	Sl. 
	Name of the transmission line
	Completion schedule

	1.
	2 X 315MVA 400/220kV Bolangir S/s

	a.
	LILO of one circuit of Sadeipalli-Kesinga 220 kV D/C line at Bolangir (PG) S/S.
	Construction of 220 kV Sadeipali- Kesinga line has started. Expected by June’18. 220 kV Sadeipali-Bolangir (PG) portion of the line is expected by June’18. 

	2.
	400/220 kV Keonjhar S/S.

	a.
	Keonjhar (PG)-Keonjhar (220/33 kV) 220 kV D/C line
	Keonjhar S/S (220/33 kV) by March’18.

	b.
	Keonjhar (PG)-Turumunga (220/132 kV) 220 kV D/C Line.
	By 2019

	3.
	400/220 kV Pandiabil Grid S/s

	a.
	Pratapsasan(OPTCL)-Pandiabil (PG) 220 kV D/C line
	March 2018 


[Action: CGM (O&M) / CGM, EHT(Const)]
C.4: Preparation of crisis management plan for Cyber Security in Power Sector in line with CERT-IN.

The activity of the preparation of Crisis Management Plan for countering the cyber attacks and its implementation including the Mock Drills, audits etc. is being monitored by CEA regularly in line with crisis management plant of Ministry of Power. Power Utilities (including generation, transmission & distribution utilities) of eastern region are to furnish regularly, the updated status to Chief Engineer, Distribution Planning & Development Division, CEA. NTPC communicated their activity of the preparation of Crisis Management Plan for countering the cyber attacks vide letter dated 2nd August, 2013.

In the 107th PSOC meeting, CGM (IT) informed that “Crisis management plan” work is awarded to M/s Digital Age Strategies Pvt. Ltd. The said firm has completed the study of Servers and Firewalls at SLDC, Bhubaneswar and back-up SLDC at Meramundali. Presently the data centers of SLDC and GRIDCO are being audited for IT security vulnerability assessment.

In the 117th PSOC meeting, CGM (IT) stated that audit has been completed and “ISO 270001 certificate”. Certificate has been issued conditionally for one year. In case OPTCL fails to fulfill the conditions, the period may not be extended. However, the audit report is yet to be received by IT.
Deliberations in the meeting

CGM (IT) stated that certificate is expected by end of February’2018.

[Action: CGM (IT) / Telecom]
C.5: Certification through BIS as per IS 18001:2007 to all generating / transmission units.
In 84th OCC meeting all constituents were requested to interact with BIS with intimation to ERPC and get certified as per CEA direction.

In the 111th PSOC meeting CGM (O&M) stated that 22 nos of officers are nominated from Chandaka, Mendhasal, Atri, Kesura, Bidanasi & Cuttack S/Ss to undergo training. Awareness training shall be started from 1st week of August’17. After receiving the price offer, order will be placed. 

In the 113th PSOC meeting CGM (O&M) stated that certification for 6 Nos of S/Ss will be done by December’2017.
In the 116th PSOC meeting, CGM (O&M) stated that draft modality has been prepared. Order for Mendhasal S/S will be issued as a pilot project.

In the 117th PSOC meeting CGM (O&M) stated that draft project report for Mendhasal S/S has been submitted to BIS. The report will be approved in the meeting to be conducted by them.

Deliberations in the meeting
O&M stated that the report has already been submitted. Approval is yet to be received.
[Action: CGM (O&M)]
C.6: Status of Disturbance Recorder, Stand alone Event Logger and Time Synchronization equipment.

The status of DR/EL and GPS as updated in previous OCCs is given below. Constituents are also requested to furnish their list of new DR/EL which are not included in the list.

[image: image2.emf]
[image: image3.emf]
[image: image4.emf]
[image: image5.emf]
In the 116th PSOC meeting, CGM (O&M) stated that EL at Meramundali sub-station for 220kV side has been installed and EL for Mendhasal sub-station has been included in the automation project. OHPC stated that DR of Indravati PH has been rectified.
In the 117th PSOC meeting CGM (O&M) stated that order for EL at Mendhasal will be placed during January 2018. It was suggested that OHPC may verify whether the DR for Indravati is included for PSDF funding and intimate ERPC.

Deliberations in the meeting
O&M stated that 400 kV side EL at Mendhasal shall be replaced. Further Order has been placed for automation of Mendhasal S/S, which is expected to be completed by end of May’2018. Proposal for including DR for Indravati is yet to be sent.
[Action: CGM (O&M) / OHPC]
C.7: Implementation of Automatic Demand Management Scheme

OPTCL vide mail dated 24.02.2016 pointed that Hon’ble CERC vide their order dated 31.12.2015 passed in Sou-motu Petition No.- 5/SM/2014 in the matter of non-compliance of Regulation 5.4.2 (d) of IEGC directed all Respondents (SLDCs) for implantation of ADMS in their respective control area. CERC have allowed dead line till 30.06.2016 to the Respondent for implementation of ADMS. Failing which they will be liable for action under Section 142 of the Act.

   *****************************************************************************

The latest status along with proposed logic as follows:
[image: image6.emf]
[image: image7.emf]
In the 115th PSOC meeting, SLDC stated that EoI document is being prepared by CPC. GM (O&M) stated that the item has not been listed in PSDF. SLDC may investigate and resend the proposal.

In the 116th PSOC meeting, CGM (O&M) stated that since considerable time has already been lapsed SLDC may prepare the EoI without waiting for CPC.
In the 117th PSOC meeting it was decided that SLDC shall process for tendering.

Deliberations in the meeting

SLDC stated that the tender specification is expected to be received from CPC by 1st week of March’2018. After receiving the same SLDC will process for tendering

[Action: SLDC]
C.8: Mock Black start exercises in Eastern Region 
The tentative schedule of black-start exercises for F.Y 2017-18 & status is as follows
	Sl.
	Name of Hydro Station
	Schedule
	Tentative Date
	Schedule
	Tentative Date

	
	
	Test-I
	
	Test-II
	

	1
	Upper Kolab
	Last week of May-2017
	Conducted on 30th May 2017
	Last week of January 2018
	Conducted on 09.01.18

	3
	Rengali
	2nd week of June 2017
	Conducted on 29.06.17
	Last week of November 2017
	Conducted on 30.11.17

	4
	U. Indravati
	3rd week of June 2017
	2nd week of July-2017
	2nd week of February 2018
	March’2018

	6
	Balimela
	3rd week of October  2017
	Conducted on 09.01.18
	1st week of March 2018
	1st week of March

	9
	Burla
	Last week of June 2017
	Can be conducted after synchronization of #2
	Last week of February 2018
	Conducted on 29th Jan’18


The black start exercise of Upper Indravati P.H. which was scheduled to be carried out on 09.01.2018 at 11:00Hrs could not be carried out due to transmission line problem and will be performed later.

[Action: OHPC / SLDC]
C.9: Less recording by Joda end energy meter of Joda _Ramchandrapur line.
Meter No NP-5937- A installed at Joda end of 220 Ramchandarpur is recording 10 % to 15 % less as compared to Ramchandarpur end since 06.12.2017. Subsequently ERLDC vide mail dated 14.12.17 (with a copy to PGCIL) requested OPTCL to check CT/PT connection to the said meter. However the problem is still persisting and GRIDCO accounting is done with Ramchandarpur end meter.

In the 117th PSOC meeting GM (O&M) stated that DGM (O&M) Joda has been advised to apply for shutdown for checking the fault and removing all unwanted meters. 

Deliberations in the meeting

O&M stated that the problem has been resolved.

C.10: Methodology for Submitting the Status of New Transmission Elements / Generating Units to be commissioned within the State

For clear visibility of the Eastern Region networks and better system operation, all the new transmission elements (ISTS & STU links) need to be updated regularly. The commissioning of new transmission elements of ISTS lines has been processed and updated by RLDC whereas commissioning of STU lines has been processed by SLDCs. However, commissioning status of new STU lines of states has not been updated to ERLDC and ERPC regularly. Sometime SLDCs used to submit the status of their new commissioning of elements during OCC meeting. To regularize the process following methodology need to be adopted:

1. Transmission elements/ Generating units expected to be commissioned during next month need to be submitted to ERLDC/ERPC in every OCC.

2. Detail parameters of new transmission element before commissioning need to be shared with RLDC.

3. Detail date and time of synchronization need to be updated on real time to ERLDC after commissioning of any new Transmission element/Generating unit.

4. SLDC SCADA team needs to configure the new element in their SCADA and share the same to ERLDC SCADA for network update.

5. List of the new transmission elements/ generating units commissioned during last month need to inform RLDC/RPC within 7th day of the current month, so that same to be updated in OCC.
It was deliberated in the OCC meeting of ERPC that the information should be sent by email in the following id:

1. erldcam@gmail.com
2. ftcer@posoco.in
3. mserpc-power@nic.in
In the 117th PSOC meeting it was decided that Sr. GM (CP) and GRIDCO shall forward the Transmission planning and Generation planning report to ERPC and other concerns as mentioned above. 
Deliberations in the meeting

It was decided that GRIDCO and CP wing of OPTCL shall submit the required information to ERPC.

[Action: Sr. G.M (CP) / GRIDCO]
C.11: Non-functioning of bus coupler breaker at Indravati PH switchyard – Other observation of Protection audit team
On 04.01.2018 3rd party protection audit party of ERPC visited the switchyard of UIHEP. The following observations were made by the team.

1. 220kV bus coupler breaker is not operating since 2013.
2. ICT tie breaker is not in service.
3. Digital PLCC panel is installed which is yet to be commissioned.
In the 117th PSOC meeting it was decided that OHPC may take necessary action for compliance of the protection audit report. OHPC may prepare the DPR if required and seek funding through PSDF.  OHPC may coordinate GM (O&M) in this regard. CGM (Telecom) stated that communication system has been approved by NLDC for PSDF funding.

Deliberations in the meeting
OHPC stated that rectifications of equipments at Indravati switch yard been included for PSDF funding. Work will be completed by January’2018. 
[Action: OHPC]
C.12: Contingency Plan to meet deficient / excess rainfall during monsoon.
The anticipated monthly demand profile in respect of various states and the annual maintenance plan of various generating units of has been received from Eastern Region. It is understood that this data is based on normal monsoon scenario. However, a poor or excess monsoon activity, sudden excess silt in the river, and such other contingencies may lead to increased demand – supply gap in the region(s) or county. Each RPC needs to be fully prepared to meet such credible contingencies.

In the above background, it is requested to estimate the impact (in terms of average MW) of various contingencies including the above ones, on the demand and availability in respect of each state/ UT for the months of June to September,2018, and an implementable action plan be prepared for handling the contingency situation like deficit or delayed monsoon, excessive monsoon, flooding of mines or damaging of railway network or situation of high silt(in the Northern Region during July-August),etc, Implementable concrete steps like identification of flexible plant outages, maintaining sufficient coal stock at critical plant sites and diversion of coal via alternate route may also be identified and documented by each RPC. Contingency arising out of failure of transmission towers also needs to be considered and preparedness by the CTU/STUs to meet the same using ERS be examined and outcome/action plan documented.

The Ministry of Power has desired that the aforesaid contingency plan be made ready by this month end.
Deliberations in the meeting
It was decided that SLDC and GRIDCO shall submit the contingency plan to ERPC.
[Action: SLDC / GRIDCO]
C.13: Approval of outage procedure and Submission of outage request to ERLDC as per procedure.

The procedure for transmission element outage was approved in 87th ERPC meeting. After this some minor modifications in the approved procedure was also done. As per the procedure following need to be adhered by the outage indenting parties while applying OCC approved transmission element outages to ERLDC for approval:

1. Request for outages which are approved by OCC must be sent by the indenting agency of the transmission asset at least 3 days in advance to respective RLDC by 10:00 hours. (For example, if an outage is to be availed on say 10th day of the month, the indenting agency would forward such requests to the concerned RLDC on or before 7th day of the month by 1000 hours.)

2. In case the request for transmission element outage is not received within the timeline prescribed above, it will be assumed that the indenting agency is not availing the outage.

However, indenting agency is duty bound to inform ERLDC at least 3 days in advance, if it is not availing the OCC approved outage.

Since last few months it was observed that some of the indenting agencies were deviating from submission dates corresponding to their OCC approval date while submitting their request, which causes a lot of inconvenience to coordinate with multiple agencies and also to carry out system study before approve the outage request. In some cases, indenting agencies were also not intimated ERLDC/ERPC in advance for cancellation of any outage approved in OCC.

Detail outage procedure as on date is updated in ERLDC website.
Deliberations in the meeting.

It was decided that SLDC & O&M shall examine the outage procedure and forward their comments to ERLDC.

[Action: O&M / SLDC]
C.14: Status of UFRs healthiness installed in Eastern Region

UFR Healthiness Certification for the month of January, 2018 has been received from CESC, WBSETCL, DVC, JUSNL, OPTCL and BSPTCL.

OCC advised OPTCL to change 33kV Laxmipur feeder with suitable feeder of desired load.


Deliberations in the meeting

It was decided that SOUTHCO shall identify other feeders having equivalent quantum of load in place of Laxipur feeder load and submit to O&M for necessary action.

[SOUTHCO / O&M]
C.15: Miscellaneous Issues.
(i)  Development of Intra-State transmission system

Intra-State transmission system needs to be planned and strengthened in a better way to avoid problems of frequent congestion.

In 30th TCC/ ERPC held on 19/20th June, 2015 constitution of Standing Committee on Transmission Planning for State Sector was approved by ERPC. In this forum of ERPC various proposals for system strengthening schemes of Eastern Region mainly under state sector/s (STU) will be discussed.
(ii) Network visualization
(a) The Communication network should be strengthened by putting fibre optic communication system. Further, the Communication network should be maintained properly to ensure reliability of data at Load Despatch Cenres.
(b) RTUs and communication equipments should have uninterrupted power supply with proper battery backup so that in case of total power failure, supervisory control and data acquisition channels do not fail.

(iii) Reduction in Start-up time for Generators
(iv) Strengthening of system study groups in various power sector organizations
There is need to reinforce system study groups in power sector organisations to analyse the system behaviour under different network status/ tripping of lines/outage of generators. Where these do not exist, these should be created.
(v) Improved telecom Infrastructure for cyber security

Deliberations in the meeting

It was decided that OHPC /O&M/ Telecom shall take necessary steps for complying the above

[Action: Telecom / O&M / OHPC]
PART-D – Operational Issues
D.1: Non-compliance of drawal schedule by DISCOMs

Non compliance of drawal schedule messages issued to Discoms during the month of Jan’18:
	Sl. No
	Name of Discom
	No. of message issued
	Over drawal (MU)
	Deviation (%)

	1
	CESU
	0
	2.615
	0.458

	2
	WESCO
	0
	-5.017
	0.829

	3
	NESCO
	0
	-0.7444
	0.174

	4
	SOUTHCO
	0
	0.093
	0.033

	
	Total
	0
	-3.0534
	


It is noticed that CESU & SOUTHCO had overdrawn during the month.
Deliberations in the meeting

All the Discoms were requested to remain in the schedule to maintain grid security

[Action: SLDC/ Discoms]

D.2: Prolonged outage of transmission elements and tentative revival dates
The tentative revival dates of transmission elements are updated in the last meeting are as follows:

	  Sl. No
	Name of transmission element
	Reason of outage
	Probable date of revival

	1
	220/132 kV, 160 MVA, Auto- 1 at Duburi
	Main tank severely damaged
	Replace by March-2018

	2
	220/132kV, 160MVA  Auto-2  at Bhadrak
	Fire hazard on 31.05.2017
	Replace by March-2018


[Action: CGM (O&M)]

D.3: Communication issues 
The status of data communication from CGPs as deliberated in the last meeting is as follows.

	Sl.
	Name of CGP
	Present status

	1
	M/s NINL, Duburi
	M/s NINL has requested for Scheme, BOQ for PLCC/SCADA, which has been forwarded by OPTCL. No action has been taken by NINL so far. 

	3
	M/s Rohit Ferrotech
	PLCC established and inspection by Telecom Engineers completed.  Database has already been prepared by OPTCL.    

	4
	VISA
	New RTU installed. Testing to be done.

	5
	Paradeep
	Duburi-Paradeep Line shutdown arranged for drawing OPGW after which data can be displayed. To be completed by January 2018.

	6
	IRE, Chatrapur
	Data communication system yet to be established by the Plant


In the 117th PSOC meeting, Members opined that GCC should file a case soon against NINL & IRE before the OERC.
GMR Issue

	GMR on line data is available at SLDC but not available directly to ERLDC. GMR entrusted the work on Powergrid.


Deliberations in the meeting

GCC stated that a case will be filed against NINL, IRE & Rohit Ferrotech for non compliance of the data communication provision.

[Action: GCC / RT&C]
D.4: Implementation of Automatic Meter Reading for OPTCL-Discom interface points.

In the 116th PSOC meeting, IT stated that out of 840 nos of meters integrated, around data from 750 nos of meters will be received each month. Data from the remaining 90 meters are to be collected manually.

In the 117th PSOC meeting IT stated that out of 840 nos of meters integrated, data from 717 nos of meters have been extracted for the month of December’17. Data could not be collected from 63 Nos of meters, which were replaced, as the information was received by IT one day before. CGM (O&M) may instruct Secure meters Ltd to inform the replacement of meters to IT immediately. 

Deliberations in the meeting
IT stated that out of 840 nos of meters integrated, data from 754 nos of meters have been extracted for the month of January’18. The extracted data will be compared with the M cubed meter reading. If found satisfactory, the project will be made go live. 
[Action: SLDC / IT]
D.5: Software for Deviation charge billing.

Hon’ble OERC may notify “Intra State Deviation settlement and related matters” Regulation at any time. For implementation of the regulation, required software for Deviation Charge billing need to be developed and tested. CGM (IT) may take necessary steps for development of the software.

As decided a committee has been constituted for development of the software in house. The work is in progress. 

In the 117th PSOC meeting IT stated that the software will be ready within a week time.

Deliberations in the meeting
IT stated that the format is being revised after changing of schedule.

[Action: CGM (IT) / SLDC]
D.6.DISCOM Issues

CESU

1. Connectivity of Ransingpur sub-station with Argul for stand by supply for Ransinghpur (connected to Chandaka S/S) from which AIIMs is availing power supply.
2. Construction of new 132/33 kV S/S at Parajang & Kantilo.
3. Providing reading status of main meter on the bill whenever the billing of an interface point of CESU is done basing on the reading of check meter.
Deliberations in the meeting
It was decided that CESU may discuss the transmission related issues with O&M through a meeting. SLDC stated that all meter serial Nos are being mentioned in the billing. CESU may go through this and contact SLDC if found any disput.

D.7: Rectification / Replacement of Defective Meters at different interface points.

A list of defective meters indicating the defects is tabled as under 
[image: image8.emf]DEFECTIVE METERS LIST

WESCO

SL NO. SUBSTATION METERING POINT MAIN CHECK REMARK

1  Bamra  Bamra Traction Feeder 132kV OPT00949 OPT01295 Active Current of one phase is negative, while the respective 

other phase current is positive. The resultant active current, is 

reduced resulting less W imp energy recorded.

2  Bamra Solar  Joy Iron Steel Ltd(Solar) XD595254 XD595255 Meter power off frequently.

3  Barapalli  Trf1-40MVA 132/33kV OPT00025 DATA COULD NOT DOWNLOADED SINCE A LONG

4  Barapalli  Trf2-20MVA 132/33kV OPT00029 OPT00032 Current in L3 become reversed frequently,showing erronous 

reading

5  Barkote SOLAR  Molisati Solar 11kV ORBP7958 ORBP7959 Meter power off frequently.

6  Bhalulata  Bhalulata Traction Feeder 132kV OPT01269 OPT00957 Active Current of one phase is negative, while the respective 

other phase current is positive. The resultant active current, is 

reduced resulting less W imp energy recorded.

7 Budhipadar Basundhara Fdr-II APM03739 APM03767 PT connection to meter need to be changed from Bus PT to line 

PT

8  Brajarajnagar  Trf2-12.5MVA 132/11kV APM02463 Meter burnt since Sept'16 needs to be changed

9  Chandiposh  Chandiposh Traction 220kV OPT01214 OPT01153 Active Current of one phase is negative, while the respective 

other phase current is positive. The resultant active current, is 

reduced resulting less W imp energy recorded.

10 Chhend  Nuagaon Traction Feeder 132kV OPT00972 OPT00966 Active Current of one phase is negative, while the respective 

other phase current is positive. The resultant active current, is 

reduced resulting less W imp energy recorded.

11  Katapali  FRP Feeder 132kV FRP_MAIN1 ORBP7511 OPTCL meter need to be installed.

12  Lapanga  Rengali Traction 132KV OPT01948 OPT01949 Active Current of one phase is negative, while the respective 

other phase current is positive. The resultant active current, is 

reduced resulting less W imp energy recorded.

13  Padmapur  Trf1-20MVA 132/33kV OPT00970 OPT00925 DATA COULD NOT DOWNLOADED SINCE INSTALLATION

14 Patnagarh ALEX Solar Pvt. Ltd. OPT00652 OPT00659 Meter power off frequently.

15  Rajgangpur  Traction Feeder-1 132kV APM03807 APM03825 Showinlg less reading in import than actual and more 

reading in export than actual.

Presently WESCO meter has been considered for 

billing,but it is not processed in ERP.It is to be manually 

added.

Need meter change urgently.

16  Rourkela  Traction Trf-12.5MVA 132/25kV OPT01009 OPT01347 Active Current of one phase is negative, while the respective 

other phase current is positive. The resultant active current, is 

reduced resulting less W imp energy recorded.

17 Sadeipali REHPL(Solar) 11kV OPT00796 OPT00731 Meter power off frequently.

18  Sonepur Solar  ABACUS HOLDINGS Solar ORBP7956 ORBP7957 Meter power off frequently.

CESU

1 Chandpur MGM SOLAR ORBP8178 ORBP8179 Meter power off frequently.

2 Kharagprasad Traction Feeder 132kV APM03744 APM03757 Active Current of one phase is negative, while the respective 

other phase current is positive. The resultant active current, is 

reduced resulting less W imp energy recorded.

3 Khurda Kaipadar Traction Feeder 132kV OPT00778 Defective since installation.

4 Paradeep PPL Feeder-I OPT00895 OPT00658 Energy recorded in export even if the ckt is isolated condition 

from PPL end.

NESCO

1 Karanjia TRF-III APM02365 Check meter showing improper voltage.The phase voltage 

varies from 12kV to 19kV,where as main meter (APM02331) 

showing correct voltage.

2 Polasponga Traction Feeder 132kV APM12622 APM12623 Active Current of one phase is negative, while the respective 

other phase current is positive. The resultant active current, is 

reduced resulting less W imp energy recorded.

SOUTHCO

1 Rayagada Traction Feeder 132kV OPT00740 OPT00714 Active Current of one phase is negative, while the respective 

other phase current is positive. The resultant active current, is 

reduced resulting less W imp energy recorded.

2 Umerkote Trf2-20MVA 132/33kV OPT00680 DATA COULD NOT DOWNLOADED SINCE INSTALLATION


OPTCL may take necessary action for checking CT / PT and early replacement of these meters wherever required.

In the 117th PSOC meeting O&M stated that a meeting has been convened on 30.01.2018 to discuss the issue. Action is yet to be taken. 
[Action: O&M / SLDC]

PART E: OPERATIONAL PLANNING
E.1:  Commissioning status of new Transmission elements. 
The status of commissioning of new transmission elements deliberated in the meeting is as follows:
	   Sl. No
	Transmission element details
	Present Status

	1
	Commissioning of 220 kV Jayanagar-Jeypore 2nd DC line 
	Work has already been started. Expected to be completed by March’18.

	2
	Commissioning of 400 kV Meramundali-Mendhasal 2nd ckt.
	Line is ready and shall be charged after commissioning of 3rd ICT at Mendhasal. Expected by March’2018.

	3
	400/220 kV, 315 MVA 3rd ICT at Mendhasal S/S
	March’18

	4
	400/220 kV, 2x315 MVA Lapanga S/S
	June’18

	5
	220/33 kV, 2x20 MVA Baliguda S/S
	December’18

	6
	220/33 kV, 2x20 MVA Kalimela S/S
	June’18

	7
	220/33 kV, 2x20 MVA Kasipur S/S
	March’18

	8
	220/33 kV, 2x40 MVA Keonjhar GIS S/S
	March’18

	9
	220/33 kV, 2x20 MVA Narasinghpur S/S
	March’18

	10
	220/132 /33 kV, 2x100 MVA Aska S/S
	June’18

	11
	220/132/33 kV, Bargarh (New) S/S (320 MVA)
	March’18

	12
	220/132/33 kV, Goda Chhak S/S (320 MVA)
	December’18

	13
	220/132/33 kV Jayapatana S/S(320 MVA)
	December’18

	14
	220/132 kV Pratapsasan S/S(320 MVA)
	March’19

	15
	220/132 kV Kesinga S/S (320 MVA)
	June’18

	16
	400 KV IB - Lapanga D/C (SEL, Bhushan & L&T)
	March’18

	17
	132/33 kV Ghense S/S
	March’18

	18
	132/33 kV Dhenkikote S/S 
	Charged on 24.02.2018

	19
	132/33 kV Betanati S/S
	March’18

	20
	132/33 kV Kantabanji S/S
	Charged  

	21
	132/33 kV R.Udyagiri S/S
	March’18

	22
	132/33 kV Chikiti S/S
	March’18

	23
	132/33 kV Athagarh S/S
	March’18


The Discoms were requested to take necessary action for availing power supply from those S/Ss and prepare their action plan for takeoff arrangement. 
[Action: CGM (Construction) / DISCOMs]
E.2: Installation of ABT compliance Energy Meter at Ib TPS feeders & Generators / Furnishing of DC

SLDC shall prepare the schedule and Energy Accounting in respect of IbTPS. It is learnt that the Main meter installed by IbTPS feeders is recording 30 minutes reading while Check meter provided by OPTCL is recording 15 minutes reading. Unless ABT compliance Main and Check energy meters installed in IbTPS feeders & Generators, the energy accounting and PAFM cannot be computed. It is requested OPTCL / IbTPS to provide ABT compliance Main and Check meters in all the 220 kV IbTPS feeders & Generators.

In the 117th PSOC meeting, it was decided that CGM (O&M), OPTCL may direct the E & MR Division, Burla to take up the work.
Deliberations in the meeting

Sr. G.M, EHT (O&M) Zone-II assured to install the meters soon.

[Action: O&M / IB TPS]    
E.3: Compliance of CEA Regulations for Grid Connectivity of Renewable Energy Sources.
As per CEA (Technical Standards for connectivity to Grid) Regulations, 2007, dated 21st February 2007, the pertinent clauses 6 (iii) & 6 (iv) (b) of general Connectivity Conditions shall be applicable to all the Generating Projects including the renewable, which are getting connected to the Grid at voltage level of 33kV & above. Subsequently, CEA have notified the CEA (Technical Standards for Connectivity of the Distributed Generation Resources) Regulations 2013 dated 30.09.2013. These Regulations are applicable for “Distributed Generation Resources”, which means A Generating Station feeding electricity into the System at voltage level below 33kV. Needless to mention that these Regulations also cover the renewable projects connected to the Distribution Licensee’s System at voltage level of below 33kV. The letter received from CEA is annexed herewith. 

SLDC has already forwarded the Regulations & a letter received from DoE, Govt. of Odisha to the Distribution Licensees.  

A meeting was convened on 29.07.2017 by Director (Commercial) between all RE Generators, SLDC, GRIDCO, DISCOMS & Telecom to decide the strategy. It was decided that the RE generators shall suggest the mechanism to be adopted for real time data communication to SLDC & Telecom to examine the same. Another meeting was proposed to be convened in the month of August’17 to finalize the mechanism of data communication. In the 113th PSOC meeting, it was decided that GRIDCO will take follow up action with all the RE generators to provide real time generation data to SLDC. ERLDC has reminded again to intimate the status.   

A meeting has been convened by Gridco in this regard with the RE generators, OPTCL, Telecom & SLDC. In the meeting, two nos of agencies presented their data acquisition logic from the RE sources. It was decided that each agency will take up a pilot project for data communication from one RE source to SLDC. On completion of the above project next course of application shall be decided.

In the 116th PSOC meeting, CGM (Telecom) stated that the solar projects need to pay the SCADA integration charges for display of the data through SCADA.

In the 117th PSOC meeting CGM (Telecom) stated that for pilot project the integration charges may not be required. The Agencies may be asked to proceed with their project.

Deliberations in the meeting

GRIDCO state that MoM has already been made for 2 Nos. pilot projects and work will be started soon.
[Action: Telecom / GRIDCO]
E.4: Major Events in the month of January’18
05/01/2018: 1 X 40 MVA, 132/33kV Tirtol Sub-station commissioned.

E.5: Important Grid Incidences during the month of January’18.
No important grid incidence occurred during the month of January 2018.

E.6: Outage of major transmission Elements during the month of January’18. (above 10 hrs).
Deliberations in the meeting

Outage of major transmission elements above 10 hours during the month was reviewed. The outages are due to conductor / jumper snapping and LA bursting.
[Action: O&M]

E.7:  Review of Outage Program of State Generators / Transmission elements for the month of Mar’18:
Tentative Outage programme for State Generators for the month of March’2018 are as follows:
	Sl.
	Station
	Unit
	Period
	Remarks

	1
	Burla
	# 5

# 6
	25.10.16 to continue

16.10.15 to continue
	Under R,M & U

Under R, M & U

	2
	Chiplima
	# 3
	15.10.15 to continue
	Under R,M & U

	3
	Balimela
	# 1

# 2

# 7
	05.08.16 to continue

20.11.17 to continue

12.10.17 to 28.02.18
	Under R,M & U

Programming for R&M

Governor problem 

	4
	Rengali
	
	
	

	5
	Upper Kolab
	# 2
	28.05.17 to 30.04.18
	Upstream leakage & intake gate Problem

	6
	Upper Indravati
	# 3
	08.02.18 to 09.03.18
	Annual Maintenance


Deliberations in the meeting

SLDC stated that due to peak power crisis shut down of Rengali unit No. 5 & 2 and Burla unit No. 2 may be deferred.   
[Action: OHPC] 
E.8: Generation Program for the month of March’18.
Generation schedule for the month of March’18 furnished by OHPC are given below. 

	Name of Hydro Gen. Station               
	Generation Program (MW)
	Reservoir Level as on 01.02.17
	Reservoir Level as on 01.02.18
	MDDL
	High Flood    Reservoir Level

	
	Mar’18
(1st fortnight)
	Mar’18
(2nd fortnight)
	
	
	
	

	HPS-I, Burla
	40
	40
	625.52 ft 
	 623.91 ft
	590 ft.
	630 ft.

	HPS-II, Chiplima
	30
	30
	-
	-
	-
	-

	Balimela
	120
	120
	1500.80 ft 
	1467.30 ft
	1440 ft.
	1516 ft.

	Rengali
	50
	50
	122.15 mt

1.78mt mtr mt
	122.25 mt mt
	109.72mtr 
	123.5 mtr.

	U.Kolab
	60
	60
	855.79 mt mt
	853.02 mt
	844 mtr 
	858 mtr.

	U. Indravati
	200
	200
	635.21 mt
	635.20 mt mt
	625mtr 
	642 mtr

	MKD (O/D)
	30
	30
	2737.85 ft 
	2745.90 ft
	2685 ft.
	2750 ft.

	TOTAL
	530
	530
	
	
	
	


Deliberations in the meeting

SLDC stated that Indravati generation will be maintained at 150 MW average to preserve water for the summer months. 
[Action: OHPC / SLDC] 
E.9: Excess water drawn by APGENCO from Balimela reservoir.
It is noticed that the reservoir level at Chitrakonda is decreasing around 0.5 ft per day due to excess water drawal by APGENCO. It is understood that the sluice gate was opened by Water Resources department to meet the irrigation requirement of AP as requested by them during January 2018. The WR department is not able to close the gate for which more water is flowing to AP resulting to depletion in the reservoir level. Necessary action has to be taken by OHPC in this regard in order to preserve water for the ensuing summer.

Deliberations in the meeting
It was decided that OHPC will investigate the issue.
[Action: OHPC / SLDC]
E.9: Anticipated power generation and demand for the month of March’2018.
	Sl. No
	Discom
	Average
	Peak

	1
	CESU
	1000
	1200

	2
	WESCO
	900
	1100

	3
	NESCO
	600
	800

	4
	SOUTHCO
	400
	600

	6
	Total Discom
	2900
	3700

	
	System Loss & others
	150
	250

	
	Total Demand
	3050
	3950

	Availability
	
	

	1
	Hydro
	530
	1350

	2
	State Thermal
	770
	770

	3
	IPP, small hydro &RE
	400
	400

	4
	ISGS share (including OA)
	1100
	1200

	5
	CGP support (OA)
	250
	250

	6
	Total availability
	3050
	3970

	7
	Surplus / Deficit
	0
	20


PART F: OTHER ISSUES

All members expressed their gratitude to Er. A.K.Behura, GM (SLDC) who is going to retire from service on superannuation by end of this month for his advice and guidance. PSOC will remember his valuable advice and the foot prints he has left for all times with deep regard.  

F.1:  Islanding scheme for GMR & IbTPS

CGM (Telecom) stated that Telecom has suggested for laying of optical fibre to implement islanding scheme for IbTPS, which is yet to be done by them. GMR IPP has no islanding scheme at present. It was decided that GMR should develop an islanding scheme for their State connected unit.

[Action: IBTPS / GMR] 

F.12:  Date and Venue of the next (119th) PSOC meeting.

The date and venue of 119th PSOC meeting will be intimated to all me

                                                         ANNEXURE
[image: image9.emf]
[image: image10.emf]
