[image: image1.jpg]QARY TQYE QA 6JNE 699

OFFICE OF THE CHIEF LOAD DESPATCHER,SLDC
ODISHA POWER TRANSMISSION CORPORATION LIMITED

PTCL GRIDCO Colony, P.0.-Mancheswar Rly. Colony, Bhubaneswar-751017, FAX-0674- 2748509
Lifeline of Odishal CIN — U401020R20045SGC007553

¥
No-SGM (PS)-PL-15/2017/ 34 &4 L > Dated: 0% .11.2018

From:

The Chief Load Despatcher
SLDC, OPTCL, Bhubaneswar-17.

To:
As per distribution list

Sub: Minutes of 126" PSOC meeting held on 27.10.2018 at PTC, Chandaka,
Bhubaneswar.

Sir,
Please find enclosed herewith the minutes of 126" Power System Operational
Co-ordination meeting held on 27.10.2018 at PTC, Chandaka, Bhubaneswar.

This is for your information & necessary action.

Yours faithfully;

Encl: As above

. AR
Chief Load Despatcher,
SLDC, OPTCL

Copy along with enclosures forwarded to the Executive Assistant to CMD, Gridco / OPTCL
for kind information of CMD.




Distribution list

1. The Director (Commercial), Gridco, Bhubaneswar

2. The Director (Operation), OPTCL, Bhubaneswar

3. The Director (Projects), OPTCL, Bhubaneswar

4. The Director (Operation), OHPC, Bhubaneswar

5. The CGM (O&M), OPTCL, Bhubaneswar.

6. The CGM (Const.), OPTCL, Bhubaneswar.

7. The Sr. G. M. (RT&C), OPTCL, Bhubaneswar.

8. The CGM (PP), GRIDCO, Bhubaneswar.

9. The CGM (IT), OPTCL, Bhubaneswar.

10. The CGM (Telecom), OPTCL, Bhubaneswar.

11. The Sr. G. M. (Const)-I, OPTCL, Bhubaneswar.

12. The C.G.M. (Const), OPTCL, Sambalpur.

13. The Sr. G.M (CPC), OPTCL, Bhubaneswar.

14. The Sr. G.M (CP), OPTCL, Bhubaneswar.

15. The Sr. G.M. (O&M), Zone-I, Narendrapur 

16. The Sr. G.M. (O&M), Zone-II, Meramundali.

17. The CEO, CESU, Bhubaneswar.

18. The A.O., WESCO, Burla

19. The A.O., NESCO, Balasore

20. The A.O., SOUTHCO, Berhampur.

21. The Member Secretary (GCC), OPTCL.

22. The ED, Power Grid Corporation of India, Bhubaneswar.

23. The Sr. G.M. (El.), BHEP, Balimela

24. The A.G.M. (El.), CHEP, Chiplima

25. The Sr. G.M. (El.), UIHEP, Mukhiguda

26. The Sr. G.M. (El.), RHEP, Rengali

27. The D.G.M. (El.), HHEP, Burla

28. The D.G.M. (El.), UKHEP, Bariniput, Koraput

29. The S.E. (O&M), Machhakund

30. The DGM (Elect.), IbTPS, OPGC, Banharpali.

31. The Vice President (O), IMFA, Choudwar.

32. The D.G.M. (O&M), NTPC (TTPS), Talcher.

33. The AGM (Elect.), JINDAL Stainless Ltd., Duburi

34. The G.M, HINDALCO, Hirakud.

35. The G.M.CPP, NALCO, Angul.

36. The Director, M/s. Jindal Steel & Power Ltd., Angul

37. The AVP-Vedanta Ltd (IPP), Jharsuguda

38. The G.M, Vedanta Ltd (CGP), Jharsuguda.

39. The DGM (Power Distribution), RSP, Rourkela.

40. Joint President, Aditya Aluminium Ltd., Lapanga, Sambalpur

41. The G.M. (Elect.),  Bhusan Steel Limited. Meramundali

42. The G.M. (Elect.), Bhusan Power & Steel Ltd, Budhipadar.
43. The G.M. (Elect.), IFFCO Limited.

44. Director & COO, GMR Kamalanga Energy Limited, Satyanagar, Bhubaneswar.

45. The CEO, Bhubaneswar Power Pvt. Ltd, IRC Village, Nayapalli, Bhubaneswar.

46. M/S Tata Power & Steel Ltd., Kalinganagar
Odisha Power Transmission Corporation Ltd. Bhubaneswar.


Minutes of 126th PSOC meeting held on 27.10.2018 at PTC, Chandaka, BBSR
List of participants is at Annexure.

Chief Load Despatcher, SLDC, OPTCL welcomed all the participants to the 126th Power System Operational Coordination meeting and highlighted the system performance during the month of September’2018 and overall power scenario of the State. He also emphasized on the drawal by all the Discoms during the month. 

G.M., GRIDCO took the agenda items for discussion. 

The review proceeded as follows: 
1: Confirmation of minutes of 125th PSOC meeting held on 20.09.2018
The minutes of meeting was circulated vide letter No. SGM (PS)-Pl-15/2017/3158(47) dated 06.10.2018 to all the members and also uploaded in the SLDC website. No comment has been received from any of the members.

Deliberation in the meeting:
Since no comments have been received from the members, the minutes of 125th PSOC meeting was confirmed. 
PART B : SYSTEM PERFORMANCE
B1: Review of Grid Performance for the month of September’2018.
(A)  Frequency 

It was noticed that, during the month of September’18, 75.23 % of times the frequency remained in the IEGC band i.e.  49.90Hz - 50.05Hz in comparison to 72.12 % during the month of  August’18. The maximum and minimum System frequency during the month was 50.10 Hz & 49.63 Hz respectively.
 (B)  Grid demand 

Grid demand for the month of  September’18 was reviewed. The average consumption during the month was 3968 MW. The maximum System demand of 4973 MW occurred on 30.09.18 at 21:00 Hrs and minimum demand of 2881 MW occurred on 21.09.18 at 05:00 Hrs. 
Deliberation in the meeting

It is observed that the average demand during the month of  September’ 18 has decreased by 286 MW and maximum demand  has decreased by 455 MW in comparison to August’18. Due to change of weather condition and power import by Vedanta Ltd through Open Access transaction, the demand has decreased during the month.
 (C) Voltage Profile of important Sub Stations in OPTCL System during the month of Sept’18.
The Voltage profile at different 220 kV buses in OPTCL system during the month of  September’18 was reviewed. 
The maximum Voltage of 235.21  kV occurred at Mendhasal 220 kV bus, while Katapali  220 kV bus has experienced the minimum Voltage of 197.56 kV. The 220 kV Voltage profile of Jayanagar and Narendrapur and 400 kV Voltage profile of Meramundali, Mendhasal  and New Duburi bus during the month of September 2018 was reviewed. 
(D) Loading of 220/ 132 kV Auto at 220 kV S/Ss in OPTCL system for the month of Sept’18.

Auto loading of all 220 kV S/Ss during the month of September’18 was reviewed. 
(E) DISCOM Drawal during the month of September’18 
The schedule and actual energy drawal by Discoms for the month of September’18 was reviewed. 
Deliberation in the meeting:
It was noticed that all the DISCOMs were over drawn during the month of September. CESU has over drawn 5.01 % followed by SOUTHCO 2.474%, NESCO 1.762% above their scheduled energy. WESCO have over drawn marginally.

.

[Action: DISCOMs] 
(F) Energy Generation / import during the month of September’18 
Energy generation and exchange during the month of  September’18 was reviewed. The total quantum of energy drawn from all the generation sources including Central Sector Share and CGP/IPP support during the month was 2857.102 MU. 
Deliberations in the meeting
The energy demand has been decreased due to less power import by Vedanta CGP through Open Access transaction.

(G) Drawal of Machhakund Power during the month of September’18
The drawal of Machhakund power during the month of September’18 was 20.039 MU, against AP drawal of 23.324 MU. 
Deliberations in the meeting

It was noticed that the State’s drawl from Machhakund is reduced since last few months. SLDC stated that due in the event of tripping of Machhakund-Podagada line, power drawl is being interrupted. As there is no communication to Podagada S/S, one CUG phone may be provided to Podagada Grid to know the status. Southco may explore for adding of more feeders to Podagada S/S. Representative from SOUTHCO was absent in the meeting to deliberate.

(H) Under Frequency relay operation in OPTCL System during the month of Sept’18.

There is no UF Relay operation during the month of September’18 as the frequency had never gone beyond 48.50 Hz. 
(I) Status of Open Access applications during the month of September’2018
Status of Open Access Applications received and disposed by SLDC during the month was reviewed.

Deliberations in the meeting
Total 154 numbers of Short Term / Medium term and Collective transaction applications have been processed by SLDC for according Approval / Consent / NoC during the month. 
PART C – Issues discussed in the 150th  OCC meeting of ERPC held on 11.10.2018

C1: ER Grid performance during September, 2018

The average consumption of Eastern Region for September-2018 was 441.4 Mu. Eastern Region achieved maximum energy consumption of 478 Mu on 29thSep -2018. Total Export schedule of Eastern region for September -2018 was 1205 Mu, whereas actual export was 809Mu. The under export of Eastern Region is mainly due to over drawl of DVC, West Bengal and Odisha 
Over drawal/under injection by ER Entities 

Over drawl figure of West Bengal and Odisha from 01-10-2018 to 07-10-2018 are shown below: 

	 
	DVC
	Odisha
	West Bengal

	
	OD (MU)
	Max OD (MW)
	OD (MU)
	Max OD (MW)
	OD (MU)
	Max OD (MW)

	01-10-2018
	3.66
	435.408
	8.35
	794.12
	1.59
	564.38

	02-10-2018
	7.05
	602.08
	7.16
	921.24
	3.70
	528.83

	03-10-2018
	5.66
	568.76
	9.30
	832.40
	3.38
	459.42

	04-10-2018
	6.20
	562.21
	8.70
	926.09
	4.66
	622.79

	05-10-2018
	10.06
	622.93
	10.26
	791.06
	0.13
	440.95

	06-10-2018
	7.98
	784.57
	2.87
	614.76
	0.83
	373.14

	07-10-2018
	1.29
	271.92
	3.60
	675.19
	1.88
	693.69


 It may be seen that for the month of the October till date,  

· West Bengal over drawl was in the range of 1 to 5 MU on daily basis while maximum over drawl touched 4.66 mu on 04-10-18 and 693 mw maximum deviation on 07-10-18. 
· Odisha over drawl was in the range of 3 to 11mu while maximum over drawl touched 10.26mu on 05-10-18 and 926 mw maximum deviation on 04-10-18. 
· DVC over drawl was in the range of 1 to 10mu while maximum over drawl touched 10.06 mu on 05-10-18 and 785 mw maximum deviation on 06-10-18. 

In 149th OCC persistent overdraw matter of West Bengal, Odisha and DVC was discussed, where in all parties were agreed to take corrective measures to avoid such persistent over-drawl. During the meeting, DVC expressed during October month their over drawl shall reduce substantially due to change on STOA sell profile and expected improvement in coal supply. Odisha also informed that due to increase in hydro generation, they would manage their drawl as per schedule during October month and west Bengal also assured to improved their internal generation and purchase profile in coming month to avoid such huge over drawl. However, for the month of September and till date October-2018 as shown above, appreciable improvement to avoid over drawal of West Bengal, DVC and Odisha was not observed. 

West Bengal, DVC and Odisha may please deliberate the reason of continuous overdrawal and future action plan to mitigate such contingency situation.  

DVC may please furnish action plan taken for improvement of coal supply issues and schedule date for restoration of plants out on coal shortage.  

Beneficiaries are also advised to maximize their internal generation and increase their power purchase quantum in STOA/Power Exchange or from any other source to maintain their drawl as per schedule.  

In case of repetitive non-compliance of ERLDC instruction to curtail over drawal during real time operation continues in future, ERLDC will have no other option but to approach appropriate commission with respect to erring entities. 
Deliberations in the meeting

SLDC stated that due to over drawl by the DISCOMs beyond the schedule, SLDC was forced to over draw from the Grid to meet their drawal. Gridco may take necessary steps for procurement of power to reduce the over drawl.

[Action: GRIDCO]   

C.2: Status of projects funded under PSDF schemes

In the PSDF review meeting, it was advised to RPCs to monitor the status of all the projects funded by PSDF. Therefore, constituents are requested to update the status of projects which are being funded by PSDF in the desired format.

The latest status as updated by OPTCL / OHPC is as given below:
	Sl No


	Name of

Constituent
	Name of Project
	Date of approval from PSDF
	Target Date of Completion
	PSDF grant
Approved (in Rs.)
	Amount

Drawn till date (in Rs.)
	Status as updated in
149th meeting

	4
	OPTCL
	Renovation & Up-gradation of protection and control systems of Sub-stations in the State of Odisha in order to rectify protection related deficiencies.
	11.05.15
	30.11.18
	162.5 Cr.


	38.09Cr. Requisition for 11.00 Cr placed.
	90% equipment installed and commissioned. Stn Tfr and some measuring instruments are under tendering process.



	7
	
	Implementation of OPGW based reliable communication at 132kV and above substations
	15.11.2017
	
	51.22 Cr
	Request for 10% grant already submitted. Agreement  signed
	Tender floated

	13
	OHPC
	Renovation & up-gradation of protection & control system of 4 nos. OHPC sub-stations
	
	U.Kolab-

March 19

Balimela-

Feb 2019

U.Indravati-Jan 19

Burla-Nov18
Chiplima

Dec 2018
	22.35 Cr.
	
	Placed work order for Balimele

	Projects under process of approval:

	
	OPTCL 
	Installation of 125 MVAR Bus Reactor along with construction of associated bay each at 400kV Grid S/S of Mendhasal,           Meramundali & New Duburi for VAR control & stabilisation of system voltage 


	28-08-17
	
	31.94 Cr
Ested. Cost. Approved amount 30.26 Cr. Grant amount 27.23 Cr.
	
	Appraisal committee recommends for project cost of 30.23 Cr and 27.23 Cr grant by monitoring committee. Agreement signed and sent to NLDC for signature. Tender floated.

	Projects recently submitted:

	
	OPTCL 
	Implementation of Automatic Demand Management System (ADMS) in SLDC, Odisha 


	22-12-17    Date of submission
	
	3.26 Cr Estt cost. 2.93 Cr recommended by Appraisal committee.
	
	Recommendation by Appraisal committee already forwarded to CERC for concurrence.

	
	OPTCL 

.
	Protection up gradation and installation of SAS for seven numbers of 220/132/33kV Grid substations (Balasore, Bidanasi, Budhipadar, Katapalli, Narendrapur, New-Bolangir & Paradeep).  
	20.02.2018  Date of submission 
	
	41.1 Cr

Estt cost
	
	Compliance to TSEG observation submitted. Audit observation has been sent to NLDC indicating justification of requirement


C.3: By passing arrangement of LILO of 400kV Lines at Angul-OPTCL

LILO of Meramundali-Bolangir/Jeypore 400 kV S/C line and LILO of one Ckt of Talcher-Meramundali 400 kV D/C line has been done at Angul 765/400kV Sub-station.

In 18th Standing Committee it was decided that Power grid would establish a switching arrangement at Angul substation such that, the above 400 kV LILO may be operated either by – passing Angul sub-station or terminating at Angul sub-station as and when required depending upon the power flow condition.

In 19th Standing Committee, it was inferred that LILOs of the above two lines needs to be by -passed to maintain the fault level at Meramundali S/S under normal operating conditions.

The necessary arrangement to be done by Powergrid for by-pass arrangement is under implementation and will be commissioned shortly.

The fault level at Meramundali will further increase after the commissioning of Meramundali​-Mendhasal 2ndckt of D/C line.

Odisha wants for normally closed arrangement at Angul so as to relieve the fault level problem at Meramundali.  Odisha further agrees that as and when the situation demands the isolator may be put in open condition.

The following standard operating procedure may be approved by the OCC for implementation of by-pass arrangement.
• The isolator will be normally closed so as to ensure the fault level at Meramundali stays within the permissible limits of 40 kA.

• Under severe contingencies like line outage or generator outage ERLDC In consultation with SLDC will open the isolator i.e.to restore the LILO of the above two lines.

Deliberations in the meeting

It was decided that CGM (Construction) shall coordinate with PGCIL to expedite bypass work.  
[Action: CGM (Const.)] 

C.4:  Establishment of Renewable Energy Management Centre (REMC) in Eastern Region---GRIDCO

Implementation of the state-of-the-art Renewable Energy forecasting & Monitormg systems is now a global best practice. For the same, it is proposed By Ministry of Power, Govt of India to establish Renewable Energy Management Centres (REMC) to address the intermittency, variability and uncertainty issues of Renewable power integration to the grid. Renewable Energy Management Centre (REMC) is part of the 'Green Energy Corridor Scheme dealt by MNRE, Gol. 
In order to facilitate integration of the targeted 175 GW of Renewable capacity by 2022, a comprehensive transmission plan is chalked out comprising of intra state and inter-state transmission system strengthening infrastructure as well as Control infrastructure i.e. establishment of REMCs at SLDC/RLDC/NLDC level.

The REMC scheme will help the grid operator to effectively manage power system operations with economy, reliability & security with an objective to forecast of RE generation on different levels such as State/ region, aggregated pooling station wise etc. based on information from Forecast Service Provider (FSP) as well as Weather Service Prov1der (WSP), Renewable Generation Scheduling, real time tracking of generation of RE sources, integration with REMC SCADA & its Visualization & close coordination with respective LDC for RE generation & integration with existing SCADA. Owner of REMC will be the existing SLDCs, RLDCs & NLDC.

At present, the REMC scheme is proposed for the Renewable rich States / regions i.e. Tamil Nadu, Andhra Pradesh & Karnataka in Southern Region. Gujrat, Madhya Pradesh & Maharastra in Western Region and Rajasthan in Northern Region co-located with SRLDC, WRLDC, NRLDC & NLDC. No REMC has been decided yet for Eastern Region & North Eastern Region. The Scheme is proposed to be financed from 100 % Gross Budgetary Support. No financial component / support is involved from the State Govts./State Discoms. 

PGCIL, the CTU will be implementing the scheme and will hand over the REMC to respective states / POSOCO upon commissioning. From the tentative State wise break up of RE generation by 2022, it can be seen that in Eastern Region also, there will be RE capacity addition of around 12, 500 MW by 2022 in Bihar, Jharkhand, Odisha, West Bengal & Sikkim.

To address the issues of RE power integration, commissioning of REMC is a necessary step. GRIDCO is proposing REMC under the 'Green Energy Corridor scheme' for Eastern Region States (to be established in ER state LDCs & at ERLDC), which need to be placed before MNRE, Govt. of India through ERPC In a relevant forum, GRIDCO has already appealed to MNRE for establishment of REMC in Odisha and MNRE has also confirmed the concern of Odisha. A combined proposal is to be submitted from ERPC to MNRE for the ER states.

Deliberations in the meeting

Director (Com), GRIDCO stated that the agenda will be discussed in the coming TCC meeting of ERPC. 
[Action: GRIDCO]

C.5: Certification of OPTCL lines as non-ISTS lines carrying ISTS power.

OPTCL vide no. RT&C-NON-ISTS/2017/281 dated 21.08.2018 had sought the Certification of non-ISTS line carrying ISTS power as per the direction of CERC in ROP dated 08.08.2018 under Petition No. 25/TT/2018. 
Accordingly, in line with 34th TCC decision, ERPC Secretariat and ERLDC conducted the load flow study using Web-Net software for all the quarters of 2014-15, 2015-16, 2016-17, 2017-18 & 2018-19 (upto Q2). 
Also, in 129th OCC held on 17.01.2017 it was decided that STU lines carrying ISTS power greater than 50% of the total power as per the Web-Net software of the validated data for each quarter will be considered as non-ISTS line carrying ISTS power. The same was also approved by 35th TCC/ERPC.

Accordingly, as per the study result it is clear that the following OPTCL lines are mostly being utilized more than 50% for carrying ISTS power, hence these elements may be considered as non-ISTS line carrying ISTS power for the tariff period 2014-19. 
	Sl.No
	Name of Line


	Remarks

	1
	400 kV Indravati-Indravati S/C
	

	2
	400 kV Rengali-Keonjhar S/C
	

	3
	400 kV Keonjhar-Baripada
	

	4
	400 kV Baripada-Kharagpur S/C
	Natural ISTS

	5
	220 kV Jeypore-Jaynagar D/C
	

	6
	220 kV Rengali-Rengali D/C
	

	7
	220 kV Balimela-U.Sileru S/C
	Natural ISTS

	8
	220 Joda-Jindal S/C
	

	9
	132 kV Joda-Kenduposi S/C
	Natural ISTS


Deliberations in the meeting

G.M RT&C suggested to make a system study by CP wing of OPTCL and list out other non-ISTS lines carrying ISTS power. SLDC shall provide the list of all inter-state lines to RT&C for reference.

[Action: Corporate Planning / SLDC]
C.6: Long Outage of transmission elements in Eastern Region

e) Breakers at 400/220kV Indravati (OHPC) S/s  

In 141st OCC, it was explained that 3x105 MVA 400/220kV ICT-I tie breaker, 220kV Bus coupler and transfer bus breakers are not in service at 400/220kV Indravati (OHPC) S/s.  

In 142nd OCC, OHPC submitted the action plan as follows: 

1. 220kV Bus Coupler: CB and CT needed to be replaced. They would restore the Bus coupler by August 2018.  

2. 220kV Bus tie: CB and CT needed to be replaced. They would restore the Bus Tie by November 2018. 

3. 400kV Tie-1 Breaker: CB and CT needed to be replaced. They would restore the 400kV  Tie-I by January 2019.  
In 149thOCC, OHPC informed that 220kV Bus Coupler had been installed and the same would be put in service inSeptember2018.
In the 124th PSOC meeting OHPC stated that 220 kV Bus coupler CB is in operational condition. Spare CT is not available for restoration of Bus coupler. Tendering for 220 kV Bus tie and 400 kV Tie –I are expected to be done by January’2019. It was suggested that OHPC may borrow CTs from OPTCL for restoration of 220 kV Bus coupler. 

In the 125th PSOC meeting OHPC stated that the CB is in service. OHPC shall coordinate with O&M for CTs.

Deliberations in the meeting

OHPC stated that they have placed the requisition for CTs before O&M. CGM (O&M0 may take necessary action.

[Action: OHPC / O&M] 

C.7:  Review of Cyber Security Works/Activities 

CEA vide letter informed that Secretary (Power) is going to review the cyber security related works /activities being carried out in Power Sector. In this regard, it is requested to provide the State wise status on following action points pertaining to cyber security at the earliest: 

 
1. Appointment of organization-wise Chief Information Security Officers and its status 

2. Identification of organization-wise Critical Infrastructure and its status 

3. Preparation of organization-wise Crisis Management Plan and its status 

4. Status of Cyber Security Mock Drill activity in coordination with CERT-In 

5. Status of Training / Workshops on Cyber Security organized / participated by power sector entities

6. Status of action taken on CERT-In / NCIIPC advisories 

In 148thOCC, all the constituents were advised to send the latest status to mserpc-power@nic.in within a week. The same has been received from WBSETCL only. 

In the 125th PSOC meeting it was deliberated that IT may request CEA to make a presentation in the PSOC meeting. 

The item could not be discussed as IT representative was not present in the meeting. IT may deliberate the status in the next meeting.

[Action: IT]

C.8: Data for preparation Load Generation Balance Report (LGBR) of ER for the year 2019-20 

As per the IEGC, RPC Secretariat is responsible for finalization of the Annual Load Generation Balance Report (LGBR) for Peak as well as Off-peak scenarios and the annual outage plan for the respective region  

To facilitate the preparation of LGBR of Eastern Region by ERPC Secretariat within the schedule period, the following data/information for the year 2019-20 in respect of the constituents/utilities of Eastern Region is urgently required: 

i) The unit wise and station wise monthly energy generation proposed from existing units during 2019-20 (thermal/hydro/RES).

ii) Annual maintenance programme for each of the generating units (thermal and hydro both).

iii)  Generating units under R&M / long outage indicating date of outage and reasons of outage and expected date of return (thermal and hydro both). 

iv) Partial and forced outage figures (in %) of generating units for the last 3 years.                                  

v) Month wise peak demand (MW) – restricted and unrestricted peak demand. i) Month wise off-peak demand (MW).  

vi) Month wise energy requirement (in MU). 

vii) Month wise & source wise power (both MU & MW) purchase and/or sale plan. ix) Schedule of commissioning of new generating units during 2019-20 and unit-wise monthly generation programme (in MU).

viii) Allocation of power from new generating units. 

ix) Month wise and annual planned outage of transmission system (Transmission lines 220kV and above / ICTs / Reactors/ other elements. 

Information may please also be submitted in the form of soft copy through email (mail ID: mserpcpower@nic.in / erpcjha@yahoo.co.in). 

In the 125th PSOC meeting all the Utilities were requested to furnish the required information to SLDC. SLDC may write a letter to all the utilities in this regard and to convene a meeting.

Deliberations in the meeting

OHPC and IBTPS stated that they have submitted their generation projection for the FY 2019-20. All Generators/GRIDCO/O&M may furnish the above data at the earliest
[Action: All generators/ IPPs / O&M/ GRIDCO/ SLDC]

C.9:  Status of Emergency Restoration system (ERS)of respective Transmission Licencees

CEA vide mail dated 28-09-2018 has requested to provide Status of Emergency Restoration system (ERS) of respective Transmission Licensees in respective Regions as per the format given below:
	State-wise Emergency Restoration system

	Transmission Licensee


	Requirement of Total

no of ERS in State


	Number of ERS

available in state


	No of ERS to

Be Procured


	Remark if any

	OPTCL
	84
	54
	30
	


Transmission Licensees may submit the details as per the format.
Deliberations in the meeting

O&M stated that they have submitted their ERS status to ERPC as mentioned above.

C.10: Delay in furnishing information to ERLDC/ERPC regarding of Commissioning of new Transmission Elements/ Generating Units within State

The above matter was deliberated in various OCC meetings and data submission format was also circulated. All states and transmission licensees agreed to submit the list of transmissions elements synchronized for the first time during last month within 7thday of the current month to ERLDC through mail. 

For the Month of September-2018, states and transmission licensees did not submit their List of Transmission element and generators synchronised in the previous month and List of Transmission element and generators expected to be synchronised during next month.

Deliberations in the meeting

AGM (Cost) stated that they are furnishing the information to ERPC each month.
C.11: Status of Implementation of islanding schemes in ER- Islanding scheme at IbTPS- OPGC 

2. Islanding scheme at IbTPS- OPGC 

The islanding scheme was discussed in 68th PCC Meeting held on 18-06-2018.  PCC opined that the draft scheme submitted by Odisha was three years old and the draft scheme is needed to be reviewed with existing network configuration.   

PCC decided to discuss the islanding scheme in next PCC Meeting and advised OPTCL to submit all the relevant details to ERPC and ERLDC.  

In 69th PCC Meeting, it was decided that ERLDC and ERPC would study and finalize the islanding scheme in next PCC Meeting.
In the 124th PSOC meeting SLDC stated that PCC sought data from SLDC to finalize the quantum of load i.e max, min and avg to be considered for islanding scheme. It was decided to convene a meeting with IBTPS, SLDC and O&M to discuss and finalize.

In the 125th PSOC meeting it was decided that O&M slall convene a meeting with IBTPS, SLDC to finalize the issue.

     Deliberations in the meeting

SLDC stated that the above issue will be discussed in the next PCC meeting of ERPC.

[Action: O&M / IbTPS]
C.12: Implementation of Automatic Demand Management Scheme

OPTCL vide mail dated 24.02.2016 pointed that Hon’ble CERC vide their order dated 31.12.2015 passed in Sou-motu Petition No.- 5/SM/2014 in the matter of non-compliance of Regulation 5.4.2 (d) of IEGC directed all Respondents (SLDCs) for implantation of ADMS in their respective control area. CERC have allowed dead line till 30.06.2016 to the Respondent for implementation of ADMS. Failing which they will be liable for action under Section 142 of the Act.

***************************************************************************

The latest status along with proposed logic as follows:
[image: image2.emf]
[image: image3.emf]
In the 116th PSOC meeting, CGM (O&M) stated that since considerable time has already been lapsed SLDC may prepare the EoI without waiting for CPC.
In the 123rd PSOc meeting SLDC stated that since the estimated cost has increased due to inclusive of SCADA integration, the revised estimate is placed in the BoD for approval

In the 124th PSOC meeting SLDC stated that the revised estimate has been approved in the BoD.

In the 125th PSOC meeting SLDC stated that CERC approval is awaited for tendering.

Deliberations in the meeting

SLDC stated that CERC approval is awaited for tendering.

[Action: SLDC]
C.13: 220 kV Inter-connecting lines of OPTCL with 400/220 kV Bolangir(PG), Keonjhar & Pandiabil S/s
PGCIL has already commissioned the 2 X 315MVA 400/220kV Bolangir S/s by LILOing of 400 kV Meramandali-Jeypore S/C line and 400/220 kV Keonjhar S/s with an objective of supplying power from ER grid to its adjoining areas in Odisha.
In 126th PSOC meeting the status has been updated as follows:
	Sl. 
	Name of the transmission line
	Completion schedule

	1.
	2 X 315MVA 400/220kV Bolangir S/s

	a.
	LILO of one circuit of Sadeipalli-Kesinga 220 kV D/C line at Bolangir (PG) S/S.
	Construction of 220 kV Sadeipali- Kesinga line has started. Expected by Dec’18. 220 kV Sadeipali-Bolangir (PG) portion of the line is expected by March’19.

	2.
	400/220 kV Keonjhar S/S.

	a.
	Keonjhar (PG)-Keonjhar (220/33 kV) 220 kV D/C line
	Keonjhar S/S (220/33 kV) by November’18.

	b.
	Keonjhar (PG)-Turumunga (220/132 kV) 220 kV D/C Line.
	By 2019

	3.
	400/220 kV Pandiabil Grid S/s

	a.
	Pratapsasan(OPTCL)-Pandiabil (PG) 220 kV D/C line
	March’2018 


Deliberations in the meeting

AGM (Const.) stated that the delay in construction of different lines is due to non-availability of clearance for Rly line crossing. RT&C suggested that the issue may be placed before the Railway meeting. SRC may be involved in the discussion.

[Action: CGM (Cont) / CGM (O&M)]
C.14: Update on status of telemetry  

CERC vide order dated 28.02.2016 on Petition No. 007/SN/2014 directed  NLDC and respective RLDCs to update the status of telemetry every month at their respective websites and take up the issue of persistent non-availability of data from Generating Stations/substations at RPC meetings for appropriate action.

In the 149th OCC, ERLDC stated that status of Breaker & isolator of NALCO & JITPL are not available.

In the 125th PSOC meeting NALCO stated that their RTU will be restored within 2-3 months. Telecom stated that Narsingpur data will be received after laying of optical fibre.

Deliberations in the meeting

Telecom stated that Service engineer of the company provided NALCO internal SCADA has arrived but could not rectified the data communication of NALCO to SLDC. Telecom suggested that NALCO may go for optical fibre for uninterrupted data communication instead of PLCC.

NALCO representative was not present in the meeting for views.

[Action: Telecom / NALCO]

C.15: Mock Black start exercises in Eastern Region 
The tentative schedule of black-start exercises for F.Y 2018-19 given by OCC is as follows
	Sl.
	Name of Hydro Station
	Schedule
	Tentative Date
	Schedule
	Tentative Date

	
	
	Test-I
	
	Test-II
	

	1
	Upper Kolab
	Last week of May-2018
	Done on 28.06.2018
	Last week of January 2019
	

	3
	Rengali
	2nd week of June 2018
	Done on 18.08.2018
	Last week of November 2018
	

	4
	U. Indravati
	3rd week of June 2018
	November’18
	2nd week of February 2019
	

	6
	Balimela
	3rd week of October  2018
	November’18
	1st week of March 2019
	

	9
	Burla
	Last week of June 2018
	Done on 07.06.2018
	Last week of February 2019
	


[Action: SLDC / OHPC]

C.16: PSS tuning of Generators in Eastern region 

Several Cases of Low frequency Oscillations have been observed in the Eastern Region. In view of this, it is desirable to have the PSS tuning of Generators in Eastern region to improve the system damping. It is mandatory as per existing CERC and CEA regulation to tune 100 MW and above generating units.  

In view of that, Generating station may kindly update the following details to ERLDC/ERPC: 

 Name of Generating Power Plant:  

	Unit

No
	Type of Excitation  System  (Static/ Brushless /Other)
	IEEE Model (IEEET1/ ESST1A/ Other)
	Name of Excitation System Vendor (ABB/GE /Hitachi/ other)
	Whether PSS is Tuned of not (If tuned Date of tuning)
	Whether Report of tuning Submitted or not

	
	
	
	
	
	


In line with regulations, all generating power plant to take up the PSS tuning activities at earliest with their vendors and submit the report after PSS tuning for verification. The response data with PSS tuning also to be shared with ERLDC/ERPC for validation in either excel or .csv format. This will be monitored in OCC on regular basis.  

OCC advised all the generators to submit the relevant data as per the format to ERLDC and ERPC. 

In the 125th PSOC meeting all Generators are requested to submit the details and inform the tentative plan for PSS Tuning to SLDC and ERPC.

[Action: All Generators] 

C.17: Preparation of crisis management plan for Cyber Security in Power Sector in line with CERT-IN. 

The activity of the preparation of Crisis Management Plan for countering the cyber-attacks and its implementation including the Mock Drills, audits etc. is being monitored by CEA regularly in line with crisis management plant of Ministry of Power. Power Utilities (including generation, transmission & distribution utilities) of eastern region are to furnish regularly the updated status to on the same to Chief Engineer, Distribution Planning & Development Division, CEA. 

In 142nd OCC, ERLDC informed that, in line with Enquiry Committee Recommendation, cyber security audit is being conducted on regular basis for SCADA system installed at ERLDC and SLDC as well but cyber security audit for telecom infrastructure installed in Eastern Region is not being carried out.  

OCC advised all the constituents to conduct the cyber security audit on telecom infrastructure installed in Eastern Region. It is further advised that compliance / mitigation of the points observed during the audit should also be completed for improvement of the telecom infrastructure in ER. 

In 37th TCC meeting, it was decided that a workshop would be conducted by CEA at ERPC for further benefit of ER Constituents.  

In 144th OCC, ERLDC informed that they have already conducted a workshop with the help of NPTI, Durgapur on 21st March 2018. 

A workshop on cyber security was conducted by CEA at ERPC, Kolkata on 09-05-2018.  

As suggested by CEA, a format would be circulated among ER constituents for furnishing the information of their respective systems for discussion in OCC Meeting. The format is enclosed at Annexure-E2. 

OCC advised all the constituents to submit the information to ERPC as per Annexure-E2.  

In the 123rd PSOC meeting IT stated that the Audit report has already been received. After depositing the required charges, audit for FY 2018-19 will be started. It was suggested that IT shall furnish the information as sought by ERPC in the required format.

In the 124th PSOC meeting IT stated that the Audit team has arrived on 27.08.18 to impart training.  

In the 125th PSOC meeting CGM (IT) stated that training has already been imparted. The required information will be submitted to ERPC.

Representative of IT was not present to deliberate. IT may deliberate the status in the next meeting
[Action: IT]
C.18: Certification through BIS as per IS 18001:2007 to all generating/ transmission units.    

In 84th OCC meeting all constituents were requested to interact with BIS with intimation to ERPC and get certified as per CEA direction.  

 As per the information received from the constituents the following generators certified with IS 18001:  

· All NTPC stations in Eastern Region  

· Teesta, NHPC 

· All OHPC generating units  

· All CESC generating units  

· All units of WBPDCL 

· DGPC units 

In the 117th PSOC meeting CGM (O&M) stated that draft project report for Mendhasal S/S has been submitted to BIS. The report will be approved in the meeting to be conducted by them.

In the 125th PSOC meeting Sr.G.M (O&M) stated that training has been completed. Mendhasal S/S audit in under progress. After compliance of the observations, certificate may be issued. 
Deliberations in the meeting

O&M stated that after compliance of the observations, certificate will be issued. 
[Action: (O&M]

C.19: Data for GEOSPATIAL energy portal of Neeti Aayog-CEA
NITI Aayog is developing a user friendly GIS based Energy Map of India, which would provide true locations of all energy resources in India including power plants, coal and oil reserves, transmission lines etc.  

CEA sought the information of name, voltage level, capacity, longitude and latitude of 33kV and 66 kV substations and lines.  

The information may be shared with CEA vide email: cedpd-cea@gov.in.  

All primary S/Ss data in respect of CESU, NESCO, WESCO & SOUTHCO has been received.

In the 125th PSOC meeting all the Discoms were requested to share the data with CEA vide email: cedpd-cea@gov.in.

Deliberations in the meeting

It was decided that SLDC shall forward the data to CEA.

[Action: SLDC/ DISCOMs]

C.20: Providing relevant data by Power Utilities / Stations in National Power Portal.

CEA vide letter dated 26th June 2018 informed that National Power Portal (NPP) (URL: npp.gov.in), has been launched by Hon'ble Minister of Power on 14th November, 2017. NPP is modified and more user-friendly data portal than the existing Information Management System (IMS) in CEA. Reports prepared from NPP are of vital importance for Power Sector data analytics in order to frame policies, regulations, future road-map for Power Sector etc. at Central as well as at State level. Accordingly, all power utilities have been issued user ID and password, either organisation-wise or station-wise, based on their request, for providing their data on NPP.

NPP has replaced IMS since 1st June, 2018. A Circular (which is available in Circular Section of CEA Website, i.e. cea.nic.in) has been issued by CEA to all power utilities/stations on 14.06.2018 for providing their data online in NPP only. 

In this regard, letters/mails have been issued to Utilities to provide their data online through NPP. 

A letter dated 20.06.2018 was also issued to all SLDC, requesting them to direct the power utilities I stations under their purview for providing data on NPP. 

Any issue/problem faced by utilities may kindly be communicated to itcea@nic.in, npp.support@gov.in, ceopm-cea@gov.in and if required, IT Division, CEA may be contacted on 011-26732368 or 011-26732303

CEA requested to pursue the power utilities / stations under their purview for providing data on NPP. 
Further, a workshop/presentation may be arranged if required in each region in which IT Division, CEA will provide a brief demonstration regarding data entering process and report generation into NPP.
Deliberations in the meeting

O&M stated that data in respect of transmission is being updated.

C.21: Load forecasting by SLDC   

For better grid management and shutdown planning, RLDCs needs to do short term load forecasting. Accuracy and effectiveness of load forecasting depend on input data. As per current practice, day ahead load forecasting is being done at ERLDC by analyzing trend previous days demand. However, for further tuning and better accuracy of load forecasting result, demand estimation from SLDCs are to be done at their end and same need to be shared with ERLDC for estimation of Eastern Region demand. 

In the 123rd PSOC meeting SLDC stated that the State demand forecasting is being done as per the drawal forecast by all the DISCOMs. The DISCOMs were requested to share their forecast methodology for intimation to ERLDC.
In the 124th PSOC meeting SLDC requested all the DISCOMs to forward their load forecast methodology by 1st week of September’2018.

In the 125th PSOC meeting Discoms stated that they are preparing their day ahead drawl forecast basing on past three days drawal with some adjustments manually. Director (Commercial), GRIDCO stated that GRIDCO will make a presentation on load forecast methodology in the next PSOC meeting. WESCO has forwarded the methodology adopted for load forecasting of WESCO. 

Deliberations in the meeting

Director (Commercial), GRIDCO deliberated the need of software for realistic demand forecast incorporating the weather condition, festive occasions and other local issues. GRIDCO have entrusted M/S ‘50 Hz’ for day ahead demand forecasting of the State. M/s ‘50 Hz’ has made a presentation and described the methodology and factors considered for demand forecasting. DISCOMs may examine and adopt a software based demand estimation methodology.
[Action: All DISCOMs]

C.22: Agenda of items to be discussed in the 72nd PCC meeting of ERPC

1. Disturbance at Bolangir (N) S/S dated 17.09.2018

2. Non operation of Auto-Recloser in the following S/S end during tripping in the month of September

a. 220 kV Joda-RC Pur

b. 220 kV Pandiabili-Samangara-II

c. 400 kV Meramundali-JSPL-I

d. 220 kV Baripada (PG)-Balasore-I 

Deliberations in the meeting

O&M may analyze for deliberation in the PCC meeting

[Action: O&M]
PART-D – Operational Issues
D.1: Non-compliance of drawal schedule by DISCOMs

Non-compliance of drawal schedule messages issued to Discoms during the month of August’18:
	Sl. No
	Name of Discom
	No. of message issued
	Over drawal (MU)
	Deviation (%)

	1
	CESU
	0
	37.164
	5.010

	2
	WESCO
	0
	4.868
	0.803

	3
	NESCO
	0
	8.235
	1.762

	4
	SOUTHCO
	0
	7.475
	2.474

	
	Total
	0
	57.742
	


It is noticed that all the DISCOMs were over drawn during the month. CESU has deviated 5.01% followed by SOUTHCO 2.474% from the scheduled energy while NESCO 1nd WESCO have deviated marginally. DISCOMs may forecast their drawal in realistic approach to minimise deviation.

Deliberations in the meeting

AO, NESCO stated that even though SLDC is providing their entitlement considering the availability of power from all sources, the DISCOMs are not able to restrict their drawl. SLDC stated that the DISCOMs should adhere to their schedule to avoid over drawl by SLDC from the Grid, which is being treated as violation of grid discipline by RLDC

[Action: All DISCOMs]

D.2: Communication issues 
The status of data communication from CGPs as deliberated in the 124rd PSOC meeting meeting is as follows.

	Sl.
	Name of CGP
	Present status

	1
	M/s NINL, Duburi
	M/s NINL has requested for Scheme, BOQ for PLCC/SCADA, which has been forwarded by OPTCL. No action has been taken by NINL so far. 

	2
	IRE, Chatrapur
	Data communication system yet to be established by the Plant


In the 117th PSOC meeting, Members opined that GCC should file a case soon against NINL & IRE before the OERC.

In the 119th PSOC meeting it was decided that GCC shall file a case against the defaulting CGP/ Consumers before the OERC. 
In the 123rd PSOC meeting it was deliberated that RT&C have sought some information from Telecom wing which will be intimated. NALCO stated that due to problem in their internal communication system, data communication to SLDC is being interrupted.
In the 124th PSOC meeting Telecom stated that communication system for Paradeep area industries will be completed by September’2018. Telecom was advised to give a reply to the information sought by RT&C. 

In the 125th PSOC meeting Telecom stated that the information sought by RT&C will be forwarded soon.

Deliberations in the meeting

It was decided that SLDC shall convene a meeting with Telecom, GCC & RT&C and discuss the issue for filing case before the OERC.

[Action: SLDC / Telecom/ RT&C] 
D.3: Implementation of Automatic Meter Reading for OPTCL-Discom interface points.

In the 116th PSOC meeting, IT stated that out of 840 nos of meters integrated, around data from 750 nos of meters will be received each month. Data from the remaining 90 meters are to be collected manually.

In the 117th PSOC meeting IT stated that out of 840 nos of meters integrated, data from 717 nos of meters have been extracted for the month of December’17. Data could not be collected from 63 Nos of meters, which were replaced, as the information was received by IT one day before. CGM (O&M) may instruct Secure meters Ltd to inform the replacement of meters to IT immediately. 

In the 118th PSOC meeting, IT stated that out of 840 nos. of meters integrated, data from 754 nos. of meters have been extracted for the month of January’18. The extracted data will be compared with the M cubed meter reading. If found satisfactory, the project will be made go live.
In the 119th PSOC meeting IT stated that Parameters of 16 Nos meters are showing wrong. DLMS data for the newly installed Secure meters are not coming. It was decided that O&M shall discuss the matter with Secure meters to resolve the issue.
In the 120th PSOC meeting IT stated that M/s Secure Meter is not responding to them. It was decided that O&M shall convene a meeting with M/s Secure meters to resolve the issue.  
In the 121st PSOC meeting it was decided that SLDC shall write CPC and OPTCL to convene a meeting with TCS and Secure meters to discuss the issue. 
In the 123rd PSOC meeting IT stated that out of 840 Nos interface meters connected with AMI, 750 Nos are reporting at present. The newly replaced meters are not reporting. 2 Nos. of meters has sent to M/s SECURE meters for study.

In the 124th PSOC meeting O&M stated that SLDC may intimate the list of defective energy meters to O&M on monthly basis for necessary action. IT may ask TCS to co-ordinate with Secure meters and develop a driver data extraction  
In the 125th PSOC meeting IT stated that they have already handed over the Meters to M/S TCS.

Representative of IT was not present in the meeting for deliberation. IT may deliberate in the next meeting
[Action: IT]

D.4: Furnishing of energy meter data for Cross Subsidy Charge billing- SLDC agenda

It is noticed that CESU is not furnishing the actual energy drawal meter data to SLDC in respect of customers importing power through inter / intra state open access transactions, even after repeated reminder from SLDC. In absence of the said data the Cross Subsidy Charge billing could not be done by SLDC in time. CESU may instruct their field engineers to furnish the data by end of 1st week of succeeding month.

Deliberations in the meeting

CESU was requested to instruct their field engineers accordingly

[Action: CESU]

D.5: DISCOM Agenda

CESU 

1. To connect 132/33KV Argul Grid S/s to 132/33KV Ranasinghpur GRID s/s in order to get stand by supply from Atri Grid S/s in case of power supply failure from Chandaka Grid or any fault in 132/33KV Chandaka – Ranasinghpur feeder, which will cater power supply to Kalinga Nagar, AIIMS, Nayapalli, Baramunda, old town, Khanadagiri area and Bhimtangi area etc.
Deliberations in the meeting
AGM (Construction stated that memorandum for the above has already been sent to Energy Deptt., GOO, for funding. A copy of the memorandum will be forwarded to CESU for reference.
[CGM(Const.) / CESU]  

2. Earlier 15minute actual drawl data was provided by SLDC, which was very much vital for giving the day ahead schedule forecast. But after stopping the DSM bill by SLDC as per order of APTEL dated 7.5.2018 passed in Appeal No.55/2015, the 15minute actual drawl data are not provided by SLDC. So, it is requested to provide the month wise actual drawl data in 15minutes block basis for giving more accurate day ahead schedule forecast by CESU.

Deliberations in the meeting

SLDC stated that CESU may collect the data from SLDC.

[Action: CESU / SLDC]

PART E: OPERATIONAL PLANNING
E.1:  Commissioning status of new Transmission elements. 
The status of commissioning of new transmission elements deliberated in the meeting is as follows:
	   Sl. No
	Transmission element details
	Present Status

	1
	Commissioning of 220 kV Jayanagar-Jeypore 2nd DC line 
	Expected to be completed by Dec’18.

	2
	Commissioning of 400 kV Meramundali-Mendhasal 2nd ckt.
	Expected by Dec’2018.

	3
	400/220 kV, 315 MVA 3rd ICT at Mendhasal S/S
	December’18

	4
	400/220 kV, 2x315 MVA Lapanga S/S
	November’18

	5
	220/33 kV, 2x20 MVA Baliguda S/S
	July’19

	6
	220/33 kV, 2x20 MVA Kalimela S/S
	July’19

	7
	220/33 kV, 2x20 MVA Kasipur S/S
	December’19

	8
	220/33 kV, 2x40 MVA Keonjhar GIS S/S
	November’18

	9
	220/33 kV, 2x20 MVA Narasinghpur S/S
	Charged on 24th August’18

	10
	220/132 /33 kV, 2x100 MVA Aska S/S
	March’19

	11
	220/132/33 kV, Bargarh (New) S/S (320 MVA)
	Charged during March’18

	12
	220/132/33 kV, Goda Chhak S/S (320 MVA)
	June’19

	13
	220/132/33 kV Jayapatana S/S(320 MVA)
	July’19

	14
	220/132 kV Pratapsasan S/S(320 MVA)
	Dec’19

	15
	220/132 kV Kesinga S/S (320 MVA)
	March’19

	16
	400 KV IB - Lapanga D/C (SEL, Bhushan & L&T)
	November’18

	17
	132/33 kV Ghense S/S
	Charged during April’18

	18
	132/33 kV Dhenkikote S/S 
	Charged on 24.02.2018

	19
	132/33 kV Betanati S/S
	March’19

	20
	132/33 kV Kantabanji S/S
	Charged on 28.02.18 

	21
	132/33 kV R.Udyagiri S/S
	December’18

	22
	132/33 kV Chikiti S/S
	(Bus test charged on 11.09.18)

	23
	132/33 kV Athagarh S/S
	Charged on 31.05.2018

	24
	132/33 kV Udala S/S
	Charged on 16.09.2018


The Discoms were requested to take necessary action for availing power supply from those S/Ss and prepare their action plan for takeoff arrangement.
Deliberations in the meeting

AGM (Const) stated that CESU is utilizing a part of 132 kV LILO line for Kalarangi S/S as 33 kV feeder, resulting connecting Kalarangi through “T” arrangement. CESU may make the line free so that the LILO arrangement will be made for Kalarangi bus. SLDC stated that this issue had been discussed in earlier meetings. CESU had assured to make the said 132 kV line free.

 [Action: CESU/ CGM (Const) / DISCOMs]
E.2: Installation of ABT compliance Energy Meter at Ib TPS feeders & Generators / Furnishing of DC

As per the provision in the Act, SLDC shall prepare the schedule and Energy Accounting in respect of IbTPS. It is learnt that the Main meter installed by IbTPS feeders is recording 30 minutes reading while Check meter provided by OPTCL is recording 15 minutes reading. Unless ABT compliance Main and Check energy meters installed in IbTPS feeders & Generators will record 15 min block energy injection,   the energy accounting and PAFM cannot be computed. It is requested OPTCL / IbTPS to provide ABT compliance Main and Check meters in all the 220 kV IbTPS feeders & Generators.

In the 119th PSOC meeting CGM (O&M) stated that Ib TPS may deposit the required amount to release meters (for check meter).

In the 122nd PSOC meeting Ib TPS stated that this has already been approved by their Authority. The required amount will be deposited soon.

In the 123rd PSOC meeting O&M stated that the required amount is yet to be deposited by IB TPS. Ib TPS have not sent their representative to the meeting for deliberation.

In th 125th PSOC meeting O&M stated that IBTPS have already deposited the required amount with O&M. O&M will release the meters soon.

Deliberations in the meeting

IBTPS stated that the meters have already been installed but not commissioned. Shut down of the line is required for commissioning of the energy meter. SLDC stated that, proposal for shut down may be sent to SLDC.
[Action: O&M/ IBTPS]

E.3: Compliance of CEA Regulations for Grid Connectivity of Renewable Energy Sources.
As per CEA (Technical Standards for connectivity to Grid) Regulations, 2007, dated 21st February 2007, the pertinent clauses 6 (iii) & 6 (iv) (b) of general Connectivity Conditions shall be applicable to all the Generating Projects including the renewable, which are getting connected to the Grid at voltage level of 33kV & above. Subsequently, CEA have notified the CEA (Technical Standards for Connectivity of the Distributed Generation Resources) Regulations 2013 dated 30.09.2013. These Regulations are applicable for “Distributed Generation Resources”, which means A Generating Station feeding electricity into the System at voltage level below 33kV. Needless to mention that these Regulations also cover the renewable projects connected to the Distribution Licensee’s System at voltage level of below 33kV. The letter received from CEA is annexed herewith. 

SLDC has already forwarded the Regulations & a letter received from DoE, Govt. of Odisha to the Distribution Licensees.  

A meeting was convened on 29.07.2017 by Director (Commercial) between all RE Generators, SLDC, GRIDCO, DISCOMS & Telecom to decide the strategy. It was decided that the RE generators shall suggest the mechanism to be adopted for real time data communication to SLDC & Telecom to examine the same.

A meeting has been convened by Gridco in this regard with the RE generators, OPTCL, Telecom & SLDC. In the meeting, two nos of agencies presented their data acquisition logic from the RE sources. It was decided that each agency will take up a pilot project for data communication from one RE source to SLDC. On completion of the above project next course of application shall be decided.

M/S Secura Meters Ltd has shown a demo for the pilot project on dated 09.07.2018. However, the data integration with SLDC VPS was not elaborated in the said demo. 
In the 123rd PSOC meeting Telecom stated that M/S Secure meters could not complete the Demo, as M/S Chemtrol requires Rs. 3.5 lacs to allow firewall access to them. M/s Chemtrol also interested to take up the work. GRIDCO may allow them for the pilot project. OPTCL may examine for Firewall access to avoid burden to the Solar projects.

In the 124th PSOC meeting it was suggested that GRIDCO may write a letter to Chemtrol for the pilot project.
In the 125th PSOC meeting GRIDCO had agreed to write a letter to M/s Chemtrol. It was decided that a committee shall be constituted with representatives of GRIDCO, O&M, Telecom & SLDC to take a decision.

Deliberations in the meeting

GRIDO may explore to constitute a committee soon. 

[Action: GRIDCO]
E.4: Major Events in the month of September’18
09.09.18: At 17:08 Hrs, 132 kV Digapahandi-Chikiti D/C line & on 11.09.18: Chikiti Bus test charged.

16.09.18: At 14:30 Hrs 132/33 kV Udala S/S charged with LILO arrangement of 132 kV Baripada-Balasore line.  

Members may note

E.5: Important Grid Incidences during the month of September’18.
There was only one Grid incident occurred during the month at Bargarh (New) Grid S/S. O&M & concern EM&R may analyze the incident for deliberation in the PCC meeting of ERPC. 
[Action: O&M / SLDC]

E.6: Outage of major transmission Elements during the month of September’18. (above 10 hrs).
Outage of major transmission elements during the month was reviewed. Most of the outages are due to conductor / jumper snapping and insulator failure.
[Action: O&M / SLDC]

E.7:  Review of Outage Program of State Generators / Transmission elements for the month of November’18:

Tentative Outage programme for State Generators for the month of November’2018 
	Sl.
	Station
	Unit
	Period
	Remarks

	1
	Burla
	# 1

# 2

# 5

# 6
# 7
	14.03.18 to 30.10.18

25.05.18 to 25.10.18

25.10.16 to continue

16.10.15 to continue
01.11.18 to 30.11.18
	T&G coupling cover water leakage

Shaft seal problem

Under R,M & U

Under R, M & U
Annual Maintenance

	2
	Chiplima
	# 1

# 3
	22.07.18 to 29.10.18

15.10.15 to continue
	Flood water inrush to turbine 

Under R,M & U

	3
	Balimela
	# 1

# 2
# 3
# 5
	05.08.16 to continue

20.11.17 to continue

26.10.18 to 20.12.18

26.08.18 to 25.10.18
	Under R,M & U

Programming for R&M
Shaft alignment & Oil leakage
PMG problem & Annual Maintenance

	4
	Rengali
	# 2
	01.11.18 to 30.04.19
	Replacement of Runner disc.

	5
	Upper Kolab
	# 2
	28.05.17 to 31.12.18
	Upstream leakage and intake gate problem

	5
	U. Indravati
	# 2
	15.11.18 to 09.12.18
	Replacement of FCB & Thyristor bridge


[Action: OHPC / SLDC] 
E.8: Generation Program for the month of November’18.
Generation schedule for the month of November’18 furnished by OHPC are given below. 

	Name of Hydro Gen. Station               
	Generation Program (MW)
	Reservoir Level as on 01.10.18
	Reservoir Level as on 01.10.17
	MDDL
	High Flood    Reservoir Level

	
	Nov’18
(1st fortnight)
	Nov’18
(2nd fortnight)
	
	
	
	

	HPS-I, Burla
	30
	30
	629.56
	630.15
	590 ft.
	630 ft.

	HPS-II, Chiplima
	20
	20
	-
	-
	-
	-

	Balimela
	150
	150
	1515.30
	1479.70
	1440 ft.
	1516 ft.

	Rengali
	40
	40
	121.61
	122.97
	109.72mtr 
	123.5 mtr.

	U.Kolab
	80
	80
	857.11
	852.63
	844 mtr 
	858 mtr.

	U. Indravati
	200
	200
	641.08
	636.02
	625mtr 
	642 mtr

	MKD (O/D)
	30
	30
	2748.10
	2745.00
	2685 ft.
	2750 ft.

	TOTAL
	550
	550
	
	
	
	


Generation schedule may change depending on inflow & availability of machine.

[Action: SLDC / OHPC]
E.9: Anticipated power generation and demand for the month of November’2018.
	Sl. No
	Discom
	Average
	Peak

	1
	CESU
	1100
	1300

	2
	WESCO
	1000
	1250

	3
	NESCO
	800
	900

	4
	SOUTHCO
	400
	450

	6
	Total Discom
	3300
	3900

	
	System Loss & others 
	150
	200

	
	Total Demand
	3450
	4100

	Availability
	
	

	1
	Hydro
	550  
	1000

	2
	State Thermal
	750
	750

	3
	IPP, small hydro &RE
	300
	450

	4
	ISGS share (including OA& purchase)
	1200
	1350

	5
	CGP support (OA)
	300
	300

	6
	Total availability
	3100
	3850

	7
	Surplus / Deficit
	350
	250


Members may discuss.

PART F: OTHER ISSUES
All members expressed their gratitude to Er. Gangadhar Patel, CGM (Safety), who is going to retire from service on superannuation by end of this month for his advice and guidance. PSOC will remember his valuable advice and the foot prints he has left for all times with deep regard.  

F.1: Absent of members in the meeting.

It is noticed that following organizations / wings have not deputed their members to represent in the 126th PSOC meeting. Some of the agenda items could not be discussed in absence of representatives of those utility/ wings of OPTCL.

1. SOUTHCO

2. NALCO

3. IMFA
4. Jindal Stainless Ltd

5. JSPL

6. TTPS

7. GMR

8. Vedanta Ltd

9. IT wing of OPTCL

Members are requested to depute their officers to represent in the PSOC meeting in future, since the forum is discussing important operational issues of the State Transmission system.     
F.2: Date and Venue of the next (127th) PSOC meeting.
ANNUXURE

[image: image4.jpg]126th Power System Operational Co-ordination Committee Meeting
[ At 11:00 A.M. on 27.10.2018]
[At PTC, Chandaka, Bhubaneswar]

'il)'. Name Designation | Organisation Mobile No. E-mail Address Signature
L AR, Des D7y (O | Gardo | TLOLOTDRTE| Abr com@gpias e, Wl
2 | B K Sale camlam| ofrcl | 9498907919 B Je
3|4, Paje) com(sy| oprer | 438907828 Ggm-%%ﬂ;@ ‘&
4 | NcSuar, com(o | orrcL | G4BTI | opmoon el LI
S| Pgsobhy | Com(u | 0PTCL |A43E0FTTE el primbe g "L Ly
6 | Kk Ageuo [Somie0 | srree | 994€99/p of \/W/
7 Pl Mishve cLb Stoe | 9418907902 e’e,ﬂ/&""lhe.s(dtmja Jb‘ f
KK Aol Geleaf] <V [a4387722] G Ay Ly
s | s P%va, Srém | Spret| qusearye)| sopan ap %6)/
10 |P-C-lo ka%m N5 (1] oF’ﬂL 4 38907220 | <le rcyg% zlf:} P
D P Kar [AaM [eto ¢ [9998907/6]:lg Fkardd] g
12 j‘)-k'?oe//;” oV cpir |9L3K76%) @Ai‘@f?@q@% A |
s | s f fedsy Jhom G 99845205 7([6’6%’/(/'(“4%
P& Celipet,| om | e 9938909900 é’%ﬁ%ﬁ&w AR
5| &R M ToL| Doy opTel |TUBS07BH el Comothon] (| oy
10 [Modhugudan Saheh Dam | GRIDCO | FET-U2E8 H, | Ao che @grmesf, M55t
17 17, & §mb) Nesco |9Y28q060(Y |Thret-Crercoadyy, ’;2}/’71/2/
18 l)\lz(/f@lvmj} Mamgcer) NESC [T 289 060 22 mg,uM@(ﬂ(mﬂ Lo <%
19 P K Nayau DaM(tel) |oprel.  |993290 TSz el prapnlapl<s &“‘%’;—,;,/
2 | R Nekey  [D4M G| SERC |9 43590754] bl prmest oty
2 Pekeep e Malepatdlf 6 | BPGHC | 93387 15Y0) }}f“;/,féfaﬂﬁh kcmmm
2]s s Bhfednl fure S Il 8 ek g
2| 5b Paccde 5 auel) B30 |apesilid epdie risgriosas | A
# DN Ftz| A M | Oftrc | 73288hooad Snpatppoohpe | RA|
= 1P Mabrpolin | GV | GUJL | F 338845 hpmeorpeOgmact] .
% ). L. Metanl™  [AOM ot & | FrLsy et mm,sfife;cwu-k,ﬂ;,/}/
7Bk padvor| A5 |07 TL] 942 9909€8 ple. b bebom Bopiicein il

| 28 &Waﬁuw‘%«\ QUM Af _/74% 793890 339 ele gw’/r’\‘_/}'i%n\rf\ M




[image: image5.jpg]Sl

No.

Name

Designation

Organisation

Mobile No.

E-mail Address

Signatu. ..

29

PLASHANT KUMARD A

Gmee

GRIDCO

q43g00F 408

pProsient .dos € Jahe <@+

b

30

SANFosH . DAL

Congutpat

Lupe.

q.4370600 261

9. Senteende € redfin

) e

iy

31

M

e

7438907935

=

32

bujajﬂ' ﬂ;/

33

34

35

36

37

38

39

40

41

42

43

44

45

46

47

48

49

50

51

52

53

54





